## Target
TIP/Accounting Section
Schedule of September-19 Month/Semester End Closing | [15 empty] | Note: Oct 4 - Japan Holiday
| Tasks / Deliverables |  | Dependency | SEPTEMBER | [7 empty] | OCTOBER
|  |  | # | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Issue September '19 Closing Schedule (FIA team) |  |  | SEPTEMBER 23: 1pm
2 | FIA's Meeting re: Sep-19 Closing preparation |  | #1
3 | Physical Inventory (snapshots)
4 | Month-end (Sep '19) Final Payments |  |  | SEPTEMBER 30: 2pm
5 | Cut-off information (Invoices and Accruals)
|  | AP Invoice |  | SEPTEMBER 30: 3pm
|  | Accruals |  | SEPTEMBER 30: 5pm
|  | Sales Cut-off information |  | SEPTEMBER 30: 4pm
|  | Receipts/Other Collection |  | SEPTEMBER 30: 7pm
6 | Physical Inventory Adjustment |  | #3 | SEPTEMBER 30: N/A
7 | PRAS Final Interface of A/P, AR, PO only (inc. Period close)
|  | AP |  | SEPTEMBER 30: 9pm
|  | AR |  | SEPTEMBER 28: 5pm (Auto Interface)
|  | PO |  | SEPTEMBER 30: 5pm (Auto Interface)
8 | GAIA Period Close - AP, AR and FA only |  | #7
|  | FA |  | SEPTEMBER 30: Keep OPEN
|  | AP |  | OCTOBER 1: 830am
|  | AR |  | OCTOBER 1: 9am
9 | Generate AP TB and AR Aging |  | #8
|  | AP TB |  | OCTOBER 1: 9am
|  | AR Aging |  | OCTOBER 1: 10am
10 | Initial Reconciliation of Cash |  | #8, #9 | OCTOBER 1: 12nn
11 | Final Interface of IA |  |  | OCTOBER 1: 2pm
12 | Manual Journals cut-off (inc. Cash reval&recon AJE, reclass) |  | #5,#7,#10 | OCTOBER 1: 5pm
13 | Review/Post Unposted Journals (inc. reclass,etc.) |  | #12 | OCTOBER 1: 6pm
14 | Mass Allocations, etc. |  | #13 | OCTOBER 1: 8pm
15 | Review of DL Cost & Expense Summary (FSG) |  | #14 | OCTOBER 2: 8am
16 | MFG PL Entries (DL+OH) / G&A / HDC (DVT/EVT+ AR) |  | #15 | OCTOBER 2: 10am
17 | Enter / Posting of On-ship Entries |  |  | OCTOBER 2: 11am
18 | TOV Change and NRV Entries |  | #16 | OCTOBER 2: 2pm
19 | Inventory Devaluation (Slow/Non-Moving) and Valuation (LCM) |  | #6, #17 | OCTOBER 2: 4pm
20 | Reconciliation of AP accounts |  | #8, #9,#13 | OCTOBER 2: 4pm
21 | Enter / Posting of Revaluation Entries (AP, AR & Other BS Monetary Accts) |  | #8-9,#13,#19-20 | OCTOBER 3: 830am
22 | Generate initial TB and review of accounts |  | #8-21 | OCTOBER 3: 9am
23 | Flash Report - PL, Inventory and Cash |  | #22 | OCTOBER 3: 3pm
24 | BS Comparative Analysis |  | #22 | OCTOBER 3: 3pm
25 | Confirmation of Cost/Expenses (Invoices - 1st 3days) |  |  | OCTOBER 3: 5pm
26 | Enter/Post AJE/Reclass (result of Flash PL & BS Analysis,Tax provision, Expense Confirmation) |  | #24, #25 | OCTOBER 4: 12nn
27 | Initial DIVA Connection (For initial checking of InterCompany) |  | #22 | OCTOBER 4: 1pm
28 | Preparation and submission of Final FS (PL, CF, BS) |  | #22- 26 | OCTOBER 4: 4pm
29 | Issuance of Expense Summary (Act vs Fcst vs Bud) |  | #28 | OCTOBER 4: 5pm
30 | Explanation of Actual Result to BODs |  | #28 | OCTOBER 7: 11am
31 | Closing of GL Period |  | #22-28 | OCTOBER 7: Keep OPEN
32 | DIVA Submission/Approval (inc. Supplemental and Questionnaires) |  | #30 - 31 | OCTOBER 7: 5pm
Items to be prepared
1 | Checklist - each group should prepare a checklist to ensure completeness of recording and reports to be submitted to HQ
2 | Confirmation of key accounts - revenue, inventory and fixed assets
3 | Comparative analysis (BS Accounts only)
4 | Expense Summary & Analysis
5 | Employees Receivable Rollforward - October 3, 3pm
Corporate DIVA Schedule: October 8, 9pm

## DIVA
TIP/Accounting Section
Schedule of DIVA Preparation
| Tasks / Deliverables |  | PIC | SEP |  |  | OCT
|  |  |  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | GAIA Period Close - AP, AR and FA only
|  | FA | Shaira | SEP 30: Keep OPEN
|  | AP | Rissa -> Buboy | OCT 1: 830am
|  | AR | She -> Buboy | OCT 1: 9am
2 | Generate AP TB and AR Aging
|  | AP TB | Jess | OCT 1: 9am
|  | AR Aging | She | OCT 1: 10am
3 | Initial Reconciliation of Cash |  | Lyn | OCT 1: 12nn
4 | Final Interface of IA |  | Cost PIC | OCT 1: 2pm
5 | Manual Journals cut-off (inc. Cash/AR reval&recon AJE, reclass) |  | PICs | OCT 1: 5pm
6 | Review/Post Unposted Journals (inc. reclass,etc.) |  | PICs | OCT 1: 6pm
7 | Mass Allocations, etc. |  | Cost PICs | OCT 1: 8pm
8 | Review of DL Cost & Expense Summary (FSG) |  | Cost PICs | OCT 2: 8am
9 | MFG PL Entries (DL+OH) / G&A / HDC (DVT/EVT+ AR) |  | Cost PICs | OCT 2: 10am
10 | Enter / Posting of On-ship Entries |  | Eugene | OCT 2: 11am
11 | TOV Change and NRV Entries |  | Cost PICs | OCT 2: 2pm
12 | Inventory Valuation and Devaluation |  | Cost PICs | OCT 2: 4pm
14 | Reconciliation of AP accounts |  | Jess | OCT 2: 4pm
15 | Enter / Posting of Revaluation Entries (AP, AR & Other BS Monetary Accts) |  | Eugene / Jess | OCT 3: 830am
16 | Generate initial TB and review of accounts |  | PICs | OCT 3: 9am
17 | Flash Report - PL, Inventory and Cash |  | PICs | OCT 3: 3pm
18 | BS Comparative Analysis |  | PIC | OCT 3: 3pm
19 | Confirmation of Cost/Expenses (Invoices - 1st 3days) |  | PICs | OCT 3: 5pm
20 | Enter & Post AJE/Reclass (result of Flash PL & BS Analysis + Tax provision) |  | PICs | OCT 4: 9am
21 | Initial DIVA Connection (For initial checking of Interco) |  | Jess | OCT 4: 10am
22 | Reconciliation of Intercompany Accounts |  | Jess | OCT 4: 5pm
23 | Enter & Post AJE/Reclass (result of Intercompany recon) |  | Jess | OCT 7: 8am
24 | Preparation of DIVA schedules (FA, AR, AP, Sales, Purchases, Landholding,etc.) |  | Jess | OCT 7: 9am
25 | Enter & Post AJE/Reclass (result of DIVA schedules) |  | Jess | OCT 7: 10am
26 | Closing of GL Period |  | Nocs | OCT 7: Keep OPEN
27 | DIVA connection |  | Jess | OCT 7: 12nn
28 | Correction of DIVA inputs (Fixed Assets, Landholding, InterCo, etc.) |  | Jess | OCT 7: 3pm
29 | Verify and check DIVA inputs |  | Nora | OCT 7: 4pm
30 | DIVA Submission/Approval (inc. Supplemental and Questionnaires) |  | Yamamoto-san | OCT 7: 5pm