## Concern or Issues Record
Concern / Issues Report
| Status: | All
| Coverage: | -
| Keyword: | %FIN%AP%
# | Control No. | Created Date | EmpNo | Employee Name | Category | Title | Description | Cause Category | Cause Detials | CounterMeasure | Status | In-Charge | Completed By | Date Completed | Acknowledged By | Date Acknowledged
1 | IT-0518-0005 | 03-May-2018 14:39 | 409M0001 | PRINCESS FAYE BAUTISTA | PRAS | Cannot find Completed Transaction in TIP QLC Transactin View | Raised by: C. Publico Date Raised: 23-APR-2018 BU: MPP Local: 3836 ISSUE: End-user concerned that they cannot find the `COMPLETED` transaction in TIP QLC Transaction View. | Bug | INVESTIGATION: 1. TIP_QLC_INTERFACE table (Data Entry of all QLC Transactions for approval) >> TIP_QLC_TRANSACTIONS ( Data Entry of all QLC Transactions that is completed or approved) >> MTL_TRANSACTIONS_INTERFACE (IF table for all transaction data to be sent to MMT) >> MTL_MATERIAL_TRANSACTIONS (table for all transaction data) 2. Completed QLC Transactions with ref_txn (540727, 540728, 540729, 540730) was not reflected in Material Transactions even there`s no error found. Per checking the TIP_QLC_TRANSACTIONS table, there is no the data that was successfully interfaced. 3. Completed QLC Transactions with ref_txn (539708, 539709, 539710, 539711, 539712, 539713), cannot be found in TIP_QLC_INTERFACE and TIP_QLC_TRANSACTIONS table but the missing transactions were already reflected in MMT. 4. Lookup table of TIP QLC Transaction View is the interfaced data in TIP_QLC_TRANSACTIONS table. Since data interfacing was unsuccessful, completed QLC transaction cannot be viewed by the end-user. | IMMEDIATE COUNTERMEASURE: 1. Performed manual subinventory transfer from HDDLINE to HDDQLC for (540727, 540728, 540729, 540730). 2. Informed user that the ff. transactions (539708, 539709, 539710, 539711, 539712, 539713) has already reflected in MTL_MATERIAL_TRANSACTIONS last 19-APR-2018 with same itemcode and QTY. 3. Initially informed end-user in case they encountered cannot view completed transactions, they can ask for the data thru ISD. FUTURE IMPROVEMENT: c/o ME-SUI Improvement of lack of QLC data Phase-1 Point of modification is to insert all the approved QLC transactions to PCM_INV_TRN_INTERFACE table instead of MTL_TRANSACTIONS_INTERFACE table. Purpose is to acquire the history of all entry data to easily investigate whenever there is lacking in QLC data | Closed | - | PRINCESS FAYE BAUTISTA | 08-May-2018 08:47 | PRINCESS FAYE BAUTISTA | 08-May-2018 08:54
2 | IT-0718-0001 | 03-Jul-2018 08:03 | 117M0001 | JOHN PAUL ABELLO | PRAS | Recovery of Re-Snapshot for SPCFIN | Raised By: F. Gorospe(PCD) Local: Transfer of PI Data from Old Snapshot Name (SPCFIN-E-0618) to New Snapshot Name (SPCFIN-E2-0618) | Spec | Unable to transfer inventory from SPCLINE-E to NCD | Perform recovery to transfer PI Data from old to new snapshot name | Closed | - | NILO ROBERTO JR. | 18-Jul-2018 07:08 | JOHN PAUL ABELLO | 18-Jul-2018 07:00
3 | IT-0718-0026 | 25-Jul-2018 08:36 | 409M0001 | PRINCESS FAYE BAUTISTA | PRAS | Cannot define new item in scrap maintenance | Date raised: 06-JUL-2018 Raised by: A.Perez BU: MPP Local: 3739 Issue: MPP cannot proceed with the definition of new item in scrap maintenance | Operation Mistake | Due to incorrect setup of item type, item code: A5A900017010 was set as `FG` instead of `Purchase Item` | Informed user to correct the setup of itemcode for HDD only. | Closed | - | EMMANUEL ANDREW TORRES | 28-Sep-2018 08:19 | PRINCESS FAYE BAUTISTA | 02-Oct-2018 10:13
4 | IT-0818-0010 | 08-Aug-2018 10:26 | 117M0021 | CHARMAINE OBLEPIAS | Application | GAC requested for editing of CAR | CARNo: OHS-17B-INT-AIF-0224 Findings/Description of Threat: Noted lapses on EPR as follows: 1. Found uninspected Safety Device, such as: 1.1 Emergency Eye Wash Inspection Tag not updated - Annex ( Forklift Area) 1.2 Fire Hose Inspection Tag not updated - Annex (MH2 Rack End Location) 1.3 Fire Extinguisher Inspection tag not updated- Annex (LOD Office) 2. Found controlled document : Emergency Information Route Chart not updated to it`s latest version. Required: Latest version color: Yellow, TIP Deputy EPR Leader not updated (LOD - FGS) Root Cause Analysis: Phenomena- Uninspected Safety Device Why1: Some safety devices not inspected Why2: Not able to find the locations of safety device Why3: (Improper way of checking) Inspection is not guided by Inspection checklist Phenomena-Not updated Information Route Chart Why1: Unable to post new Chart Why2: Mis-placed the provided chart for posting Why3: DSO endorsed it to the leader of the Area Corrections/Immediate Actions: -Inspected all missed out safety devices. -Replaced the old information route chart with new one Corrective Actions1: 1. Assign fixed person from EPR team per area to perform the monthly inspection and use printed checklist as guide to find the locations of each device and quantity. 2. Include in the Safety device inspection checklist the location and Qty of Information Route chart similar to Evacuation map. | Spec | User requested to modify the CAr details because they can`t edit. | replaced the details save on the database | Closed | - | CHARMAINE OBLEPIAS | 15-Nov-2018 11:28 | CHARMAINE OBLEPIAS | 15-Nov-2018 11:35
5 | IT-0918-0002 | 04-Sep-2018 14:51 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN ¦ XX00IFAR Interface Error ¦ Performed rollback for 7 AP Bathces with errors in GAIA | Raised By: C. Castillo Loc. 3584. All batches did not interface in GAIA due to mismatched of data in batches (APCMNEBS_20180813_001, APCMNEBS_20180813_002, APCMNEBS_20180813_003, APCMNEBS_20180813_004, APCMNEBS_20180813_005, APCMNEBS_20180813_006 and APCMNEBS_20180813_007) Batch 1 (APCMNEBS_20180813_001) encountered an error due to twice in request of AP Invoice Data File Creation Program. All batches were pending due to error encountered. | Operation Mistake | Twice in request of AP Invoice Data File Creation Program. All batches were pending due to mismatch in FTP File name upon interface to GAIA | Rollback all transactions and run conversion --> File transfer program | Closed | - | PATRICIA LUNA | 01-Oct-2018 08:10 | JOHN PAUL ABELLO | 04-Oct-2018 07:30
6 | IT-0918-0003 | 04-Sep-2018 14:23 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN ¦ AP SOURCE CODE ¦ Request for setup for new AP Source Code in PRAS | Raised By: I. Ponado Loc. 3582 Request for additional AP Source Code setup in PRAS Already requested and completed in setup in GAIA. T090593_000_0054 Z7126TIP Invoices Created by Eugenia Gallor T090593_000_0055 Z7112TIP Invoices Created by Shaira Recreo T090593_000_0056 Z7105TIP Invoices Created by Carlo Castillo | Spec | Request for additional AP Source Code setup in PRAS | N/A | Closed | - | JOHN PAUL ABELLO | 22-Jan-2019 15:47 | JOHN PAUL ABELLO | 22-Jan-2019 15:56
7 | IT-1018-0001 | 01-Oct-2018 08:09 | 115E0017 | PATRICIA LUNA | PRAS | EHD ¦ RFA ¦ Redirect approver1 for EHDFIN RFA Transactions | Raised by: Abigael Pablo (EPP) Local: 5351 Raised date: September 28, 2018 EPP raised a concern that incorrect approver 1 was selected, current approver 1 is on leave. Since RFA transactions are necessary for physical inventory, business user requested to redirect the approval. | Operation Mistake | Incorrect selection of approver. Selected approver is on leave. | N/A | Closed | - | NILO ROBERTO JR. | 23-Jan-2019 13:19 | NILO ROBERTO JR. | 19-Feb-2019 07:08
8 | IT-1218-0013 | 18-Dec-2018 08:35 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AR ¦ AR INTERFACING ¦ Customer site code error | In manual PO creation, Bill To site was changed to TOSHIBA MEMORY CORPORATION, but during interface to GAIA, changes did not apply. Encountered AR interface error because bill to customer set up was toshiba corporation instead of toshiba memory corporation | Operation Mistake | PO Bill to site data contained TOSHIBA CORPORATION customer name, but correct customer site was TOSHIBA MEMORY CORPORATION | Correct XX00IFAR_TRX_HDR_STG_ALL bill to site data for transaction to interface to GAIA. | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:01 | JOHN PAUL ABELLO | 04-Jan-2019 14:10
9 | IT-1218-0015 | 18-Dec-2018 08:38 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ XX00IFAP INTERFACE ¦ Number of invoice in one batch is not correct | Raised By: E.Gallor (FIA) Loc. 3010 Rollback of invoices included in T090593_000_0029 batch under source code APCMNEBS_20180919_001 Processed 2 batches in one execution of file creation -> File Transfer that caused mismatch of data | Operation Mistake | Processed 2 batches in one execution of file creation -> File Transfer that caused mismatch of data | Transaction must be cancelled in GAIA and need to be interfaced again in PRAS AP | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:25 | JOHN PAUL ABELLO | 04-Jan-2019 14:36
10 | IT-1218-0017 | 18-Dec-2018 08:03 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ IMPEX ¦ IMPEX transaction that did not interface in AP | Raised By: E.Gallor (FIA) Invoice: TLF-09-18P2 did not reflect in AP interface upon request of Payables Open Interface Import | Bug | Cause is not yet determined but upon checking, Invoice did not interface in AP but the current status in IMPEX is already approved | Rollback transaction and re-approve from IMPEX to AP | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:22 | JOHN PAUL ABELLO | 04-Jan-2019 14:33
11 | IT-1218-0018 | 18-Dec-2018 09:43 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ XX00IFAP INTERFACE ¦ BU Processed conversion with error during extraction | Raised By: E.Gallor (FIA) Rollback of invoices that were interfaced in GAIA batches APCMNEBS_20180929_001 and APCMNEBS_20180929_002 PIC processed Conversion --> File Transfer eventhough it has error in Extraction | Operation Mistake | PIC processed Conversion --> File Transfer even though it has error in Extraction | Rollback affected invoices and re-interface to GAIA | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:56 | JOHN PAUL ABELLO | 04-Jan-2019 14:03
12 | IT-1218-0019 | 18-Dec-2018 09:03 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ AP Staging Table ¦ Clean up of AP invoices with errors in XX00IFAP STG table | Raised By E.Gallor (FIA) There are numerous number of pending transaction in AP staging table and somehow affects other batches when error has been resolved. These invoices was already interfaced already by creating a manual invoice entry and invoices with error are still pending | Operation Mistake | Cancelled invoices in AP standard are not cancelled in PRAS staging table. FIA recreate correct invoices by appending character at the end. Invoices with errors remains in staging table. | Clean up all cancelled invoices in staging table. | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:50 | JOHN PAUL ABELLO | 04-Jan-2019 14:00
13 | IT-1218-0020 | 18-Dec-2018 09:14 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_IA ¦ RFA ¦ Incorrect RFA FIA Approver | Raised By: E.Leyban (FIA) Adjustment for SPCLINE-E must be assigned to new FIA member. New FIA Approver was not updated in tip_default_values before RFA transaction was made in TIP_RFA_INTERFACE. | - | - | - | Denied | - | - | - | - | -
14 | IT-1218-0021 | 18-Dec-2018 09:25 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ AP Source Code ¦ Set up of new AP source code in PRAS | Raised By: I.Ponado (FIA) Request for additional AP Source Code setup in PRAS Already requested and completed in setup in GAIA. T090593_000_0057 ; Z7216TIP ; Invoices Created by Sherilyn Malijan | Spec | New PIC for AP | For set up of new AP source code | Closed | - | JOHN PAUL ABELLO | 04-Jan-2019 14:36 | JOHN PAUL ABELLO | 04-Jan-2019 14:43
15 | IT-1218-0023 | 18-Dec-2018 09:47 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ XX00IFAP INTERFACE ¦ Cancellation of AP invoice not interfaced in GAIA | Raised By: S.Malijan (FIA) Cancellation of invoice number CR-MPE-1218-0001 that was not interfaced to GAIA. Will re-process this invoice in a seperate batch. Related invoice were hang in staging table of AP and need to cancel to proceed with interface to GAIA. | Bug | Cancelled invoices in AP are not cancelled in PRAS staging table | Cancel affected invoices in PRAS staging table | Closed | - | JOHN PAUL ABELLO | 22-Jan-2019 13:17 | JOHN PAUL ABELLO | 22-Jan-2019 13:27
16 | IT-1218-0024 | 18-Dec-2018 09:04 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AR ¦ TIP AR AUTO DN/CN ¦ No Workflow was sent with BS transaction | Raised By: D.Soledad(MME) Cancellation of one BS transaction number 1812 BS#0000359. To avoid duplicate application in DNCN system, transaction is needed to be cancelled. Reason is WF notification was not sent to approvers. | Bug | No workflow found in WF_NOTIFICATIONS. Cause is still for checking | countermeasure is to re-apply transaction and cancelled previous transaction | Closed | - | JOHN PAUL ABELLO | 22-Jan-2019 13:44 | JOHN PAUL ABELLO | 22-Jan-2019 13:04
17 | IT-1218-0025 | 18-Dec-2018 09:49 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_IA ¦ RFA ¦ Incorrect RFA FIA Approver | Raised By: G.Tidalgo (FIA) Adjustment for SPCLINE-E must be assigned to new FIA member. New FIA Approver was not updated in tip_default_values before RFA transaction was made in TIP_RFA_INTERFACE. | Setup Mistake | New FIA Approver was not updated in tip_default_values before RFA transaction was made in TIP_RFA_INTERFACE. | Update tip_rfa_interface to correct FIA approver | Closed | - | JOHN PAUL ABELLO | 22-Jan-2019 13:05 | JOHN PAUL ABELLO | 22-Jan-2019 13:14
18 | IT-0219-0009 | 22-Feb-2019 15:06 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ Payables Open Interface Program ¦ Invalid Distribution Account | Raised By: S. Malijan (FIA) Upon running of Payables Open Interface program, Two invoices were rejected due to invalid distribution account. | Spec | Code combination was end dated. Enabled flag is `N` | Enable code combination set up in gl_code_combination | Closed | - | JOHN PAUL ABELLO | 04-Mar-2019 09:17 | JOHN PAUL ABELLO | 04-Mar-2019 09:27
19 | IT-0219-0010 | 22-Feb-2019 15:02 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ TIP Last Pay Uploading ¦ Wrong Cost Center Uploaded | Raised By: S. Malijan (FIA) Upon uploading of data for globe billings, Error message appeared. "Wrong Cost Center Uploaded" cannot proceed with transfer to AP | Spec | As per checking, cost center is new. No set up in TIP default values. | Proceed with set up in TIP default values | Closed | - | JOHN PAUL ABELLO | 04-Mar-2019 10:47 | JOHN PAUL ABELLO | 04-Mar-2019 10:57
20 | IT-0519-0002 | 09-May-2019 08:04 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN ¦ GL-Payroll ¦ Recovery of Payroll transaction in GL Interface-GAIA | Raised by: (HRD) M. Niadas Wrong Declaration of Amount in New Gasoline allowance There is a set-up wrong of amount of New gasoline Allowance in Managers Payroll this April 30, 2019 due misunderstanding of the exact amount to be declared for April 30, 2019 Managers Payroll | Operation Mistake | Incorrect set up in amount | Exclude the transactions with incorrect amount in XX00IF tables | Closed | - | JOHN PAUL ABELLO | 23-May-2019 17:45 | JOHN PAUL ABELLO | 23-May-2019 17:51
21 | IT-0519-0003 | 09-May-2019 08:24 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN ¦ GL-RCV ¦ Recovery of GL-RCV Batch with null cr_dr_flag | Raised By: (MPD) Y. Calubayan (FIA) E.Gallor Encountered zero unit price withdrawn under eSSD BU last Apr 28, 2019. CR_DR_FLAG was set to null while interfacing to GAIA. Hence error occurred in the batch | Operation Mistake | Unit price of 1 item is 0.0045 and only two decimal places was captured by XX00IF Ext-Conv Program resulting to 0.00 or 0 | Rollback GLCMNEBS_20190429_002_L.dat and re-process excluding the item with zero unit price | Closed | - | JOHN PAUL ABELLO | 23-May-2019 17:06 | JOHN PAUL ABELLO | 23-May-2019 17:11
22 | IT-0519-0008 | 16-May-2019 15:45 | 117L0003 | RON EZREL DE VILLA | PRAS | MFG_SSD¦Physical Inventory¦Transfer Inventory Data from SSD-FIN-0319 to SSD-FIN2-0319 | BU: M. Calili DEPT: SSD Duplicated Data interface on item code KXG6AZNV256GAP1MDA during line to count processing. | Bug | During line to count processing there is encountered network disconnection. Upon re-uploading previous data uploaded before network disconnect was successfully insert in Oracle which cause of some variance for some parts during second uploading. ( See the attached file above for your reference ) | Transfer the old physical inventory item id to new snapshot physical inventory excluding the first uploaded data | Closed | - | RON EZREL DE VILLA | 04-Jun-2019 09:43 | RON EZREL DE VILLA | 04-Jun-2019 09:52
23 | IT-0619-0004 | 13-Jun-2019 17:34 | 409M0001 | PRINCESS FAYE BAUTISTA | PRAS | PUR¦BPO¦ Cannot find BPO for approval | Raised by: W. Leyba Date Raised: 04-JUN-2019 BU: MMW Issue: Cannot find BPO for approval | Operation Mistake | End user selected the `FIND` radio button instead of `APPROVAL` | 1. Check Approval Hierachy MST - OK 2. Check BPO (Pending Approval) - OK, exist 3. Check email setup - OK | Closed | - | PRINCESS FAYE BAUTISTA | 03-Sep-2019 14:39 | PRINCESS FAYE BAUTISTA | 03-Sep-2019 14:50
24 | IT-0719-0006 | 05-Jul-2019 07:31 | 117L0003 | RON EZREL DE VILLA | PRAS | FIN_AP¦Impex Invoice Uploading¦Rollback of invoice transacted from IMPEX | BU: S. Malijan DEPT: FIA Description: Rollback of invoice number FDX-06-19P4 transacted from IMPEX.Related invoice did not interface from IMPEX and need to re-approve transaction | Bug | Rollback of invoice number FDX-06-19P4 transacted from IMPEX. Related invoice did not interface from IMPEX and need to re-approve transaction | 1. Rollback Transaction from Impex - c/o ISD 2. Re-approve transactions in Impex - c/o FIA 3. Check if already exist in AP Interface - c/o FIA & ISD See the above attached file for your reference. | Closed | - | RON EZREL DE VILLA | 10-Jul-2019 13:38 | RON EZREL DE VILLA | 10-Jul-2019 13:51
25 | IT-0719-0007 | 05-Jul-2019 07:14 | 117L0003 | RON EZREL DE VILLA | PRAS | FIN_AR¦DN/CN Application¦To recover approved BS which failed to interface due to NULL accounting charging (1906 BS#0000657) | BU: C. ROCETA DEPT: FIA DESCRIPTION:To recover approved BS which failed to interface due to NULL accounting charging (1906 BS#0000657). Failed to interface due to NULL Accounting Charging | Operation Mistake | Failed to interface due to NULL Accounting Charging in AUTO DN/CN Application. | Update the AR related tables and DN/CN Tables. See the actual operation evidences on the issue sheet attached above. | Closed | - | RON EZREL DE VILLA | 10-Jul-2019 13:57 | RON EZREL DE VILLA | 10-Jul-2019 13:09
26 | IT-0719-0013 | 10-Jul-2019 13:30 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ Payables Open Interface ¦ Invalid Distribution Account | Raised By: R.Ernacio (FIA) Upon running of payables open interface. 2 invoices encountered error in data regarding distribution account. Note that this invoice was uploaded using Portal team`s web application. | Spec | AP invoices lines has 0 value in AP_INVOICE_LINES_INTERFACE.DIST_CODE_COMBINATION_ID Cause is no set up in PRAS for the selected charge of account. | FIA must check first the code combination if already set up in PRAS. As per web team, there`s a functionality in the program where they can check if the COA is existing or not. | Closed | - | JOHN PAUL ABELLO | 17-Jul-2019 08:49 | JOHN PAUL ABELLO | 17-Jul-2019 08:55
27 | IT-0719-0020 | 19-Jul-2019 10:56 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ PRS Liquidation ¦ Travel/CA/CR: Pls. check GL Code Set Up | Raised By: I.PONADO ( FIA) Description: Cannot proceed with uploading of PRS transaction due to code combination set up for a specific employee. | Setup Mistake | Error was related to set up 1. No set up in GL_CODE_COMBINATION for HDC department. 2. Set up of employee was also correct (as per FIA, HDC site code was transferred to CIP) | (HRD/FIA) should inform ISD for any changes so that it will not encounter error upon any transactions | Closed | - | JOHN PAUL ABELLO | 31-Jul-2019 13:04 | JOHN PAUL ABELLO | 31-Jul-2019 13:13
28 | IT-1019-0010 | 02-Oct-2019 10:50 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_IA ¦ Auto DNCN ¦ Change DNCN Accounting Checker | Raised By: Gay (FIA) Change of approver for all HDD Billing Statements/DNCN (M10) from E. Leyban (z1270tip) to G. Tidalgo (z6191tip) | Spec | N/A | N/A | Closed | - | JOHN PAUL ABELLO | 28-Oct-2019 09:24 | JOHN PAUL ABELLO | 28-Oct-2019 09:47
29 | IT-1019-0011 | 02-Oct-2019 10:42 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_IA ¦ RFA ¦ Change RFA FIA Accounting approver | Raised by: G.Tidalgo (FIA) Change of accounting approver for ESD, ESP, and NED from G. Tidalgo (z6191tip) to C. Roceta (z6992tip) Change of RFA accounting approver for HDD, HPC, DSM, NHD, NND and NAD from E. Leyban (z1270tip) to G. Tidalgo (z6191tip) Effectivity : October 2019 | Spec | Request to change RFA approver. | N/A | Closed | - | JOHN PAUL ABELLO | 08-Nov-2019 10:09 | JOHN PAUL ABELLO | 08-Nov-2019 10:22
30 | IT-1019-0017 | 25-Oct-2019 10:55 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ Create Invoices for Payments(IMPFT010) ¦ null account segment in create invoices (IMPEX) | Raised by: M.Cusi (LOD) Cannot proceed create invoices from IMPEX to AP. There were uploaded invoices with null account segment. | Spec | create button is disabled if account segments / code combination id is null Upon checking of program._x00B_Null was inserted due to duplicate set up in TIP_DEFAULT_VALUES:_x00B_Error: Exact fetch more than requested rows | Update TIP Default Values. Disabled old cost center | Closed | - | JOHN PAUL ABELLO | 14-Nov-2019 10:02 | JOHN PAUL ABELLO | 14-Nov-2019 10:09
31 | IT-1119-0005 | 08-Nov-2019 13:18 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ TAPF0002 (SSS Maternity) ¦ Wrong Cost Center Uploaded | Raised By: S.Malijan (FIA) Encountered error upon running TIP Lastpay system -> Upload Employee data for SSS Maternity Payment. Wrong cost center was uploaded | Spec | NO SET UP IN TIP DEFAULT VALUES New cost center for 19B Table Name: TAPF0002 Field Name : SECTION | Proceed with set up in default values every after change of cost center every sem. | Closed | - | JOHN PAUL ABELLO | 15-Nov-2019 15:45 | JOHN PAUL ABELLO | 15-Nov-2019 15:51
32 | IT-1119-0006 | 08-Nov-2019 14:58 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ Subledger Accounting Program Report ¦ M20 Balancing Segment cannot be used | Raised by: S.Malijan (FIA) New SBU: M20 Upon Execution of Create Accounting Concurrent program. Error encountered in Subledger Accounting Program report. It contains lines with balancing segment values that are not assigned to any legal entity: T090593 -> Local and IFRS | Spec | No set up of New SBU M20 in Balancing Segment Values for Ledger: T090593_TIP_LOCAL No data in ---> select * from GL_LEDGER_SEGMENT_VALUES where segment_value = `M20` | Proceed with set up. Need to consider this set up for future changes in SBU set up. | Closed | - | JOHN PAUL ABELLO | 13-Nov-2019 07:25 | JOHN PAUL ABELLO | 14-Nov-2019 07:28
33 | IT-1119-0007 | 08-Nov-2019 15:25 | 117M0001 | JOHN PAUL ABELLO | PRAS | FIN_AP ¦ SSS Maternity (SP_SSSMAT_AP_VALIDATE) ¦ No Data Found | Raised By: T.Daza & V.Aguado (Web Team) Cannot proceed with uploading of SSS Maternity from web application to AP PRAS. No data found was encountered in line 227 for SP_SSSMAT_AP_VALIDATE package. | Spec | NO SET UP IN _x00B_TIP_DEFAULT_VALUES for new SBU_x00B__x00B_ TABLE NAME: TAPF0002_x00B_ FIELD_NAME: SECT_BU | Proceed with set up and will also consider this set up if there`s any changes in cost center. | Closed | - | JOHN PAUL ABELLO | 15-Nov-2019 17:53 | JOHN PAUL ABELLO | 15-Nov-2019 17:00
34 | IT-0220-0008 | 26-Feb-2020 09:58 | 409M0001 | PRINCESS FAYE BAUTISTA | PRAS | TIP IA01779_Recovery of PR Approval Hierarchy for MQA4 | Raised: M. Medrano BU: MME Date Raised: 2/19/2020 Issue in MQA4 Hierarchy flow last march 2018. There is a pending for approval. But due to organizational change PIC in pending for approval transfer to other site that’s why pending for approval last for years ago.(March 22, 2018). Cannot find on the worklist the notif for approval. | Operation Mistake | Workflow notification has been expired due approver did not take action for since March 2018. | Manual update of affected tables so end-user can revise the approval hierarchy again. | Closed | - | PRINCESS FAYE BAUTISTA | 05-Jun-2020 09:18 | PRINCESS FAYE BAUTISTA | 05-Jun-2020 09:27
35 | IT-0820-0003 | 11-Aug-2020 10:39 | 117M0001 | JOHN PAUL ABELLO | PRAS | MFG_EHD ¦ CCPH CALCOMP ¦ Return old cartons from EHDLINE-A to EHDFIN | Raised by: V.Calderon (EPP) Request to return cartons from CCPH to EHDFIN due to unpack/rework. Concern is that affected cartons are dated 1 year ago. Cannot transaction in application due to prompt message "Carton does not exist in Packing System" | Spec | Old cartons are for transaction. obsolete | No recovery. perform standard Misc issue/ Misc receipt transactions c/o EPP | Closed | - | JOHN PAUL ABELLO | 08-Sep-2020 07:40 | JOHN PAUL ABELLO | 08-Sep-2020 07:45
36 | IT-0121-0001 | 14-Jan-2021 07:01 | 119G0008 | PAULENE MAE PANGILINAN | PRAS | HRMS¦PAYROLL¦Assignment Set name not found | Used assignment set not found in Final Pay Process "\\tip-fs-004\Public-ISD\ISD-IS3-Application\IS3 System Support\PRAS and HRMS Support\ORACLE HRMS\HRMS\Common Troubleshooting\Errors and Issues Logs 2020\02. PAYROLL\01. LOCAL PAYROLL\Assignment Set Name not found.xlsx" | Operation Mistake | Incorrect naming of assignment set used in lastpay processing | Rechecking of lastpay assignment set; make sure it follows the standard naming convention TIP_LASTPAY_% | Closed | - | PAULENE MAE PANGILINAN | 15-Jan-2021 07:59 | PAULENE MAE PANGILINAN | 15-Jan-2021 07:09
37 | IT-0521-0007 | 24-May-2021 15:05 | 120J0001 | JOHN VINCENT AJERO | Application | PUR ¦ PR Approval ¦ PR already approved but status is still IN PROCESS | PR already approved by final approver but due to error in workflow, PR is stuck in In Process status. | - | - | - | Denied | - | - | - | - | -
38 | IT-1021-0002 | 08-Oct-2021 09:12 | 117L0003 | RON EZREL DE VILLA | PRAS | FIN_AP¦ Conversion Execution ¦ the account corresponding to currency_code is not found | BU: R. Ernacio DEPT. FIA Encounter error "*****1-41XXGFAAU_CHK_B65_10005the account corresponding to currency_code is not found..Source AFF: T090593.A99.L10.0000000.20201110.2232.00000.PHL.0000000.000000.0000" after execution of conversion program | Setup Mistake | Invoice Currency code in GAIA maybe not setup in USD( we don`t have access to GAIA only FIA). So we ask FIA to check the setup of currency code of the affected customer. Only PRAS setup is correct and currency code is set to USD. | See countermeasure sheet on the above attached file. | Closed | - | RON EZREL DE VILLA | 14-Oct-2021 08:46 | RON EZREL DE VILLA | 14-Oct-2021 08:53
39 | IT-1021-0005 | 20-Oct-2021 11:09 | 117L0003 | RON EZREL DE VILLA | PRAS | FIN_AR¦ DNCN ¦ Cannot Find Approver in PRAS DNCN Application | BU: E. Ricalde Dept: PCB Description: Sir elmer is not included as approver in PRAS DN/CN Application. | Setup Mistake | Sir Elmer Doesn`t have TIP AR AUTO DN/CN Responsibility on his Oracle Account | Inform User to create helpdesk request to add TIP AR AUTO DN/CN Responsibility on sir elmers account( see attached file above on the countermeasure sheet) | Open | RONNEL MONTANEZ | - | - | - | -
40 | IT-1121-0016 | 23-Nov-2021 07:10 | 117L0003 | RON EZREL DE VILLA | PRAS | FIN_AP ¦ SSS ¦ Error upon generating SSS PRF in Portal | BU: C. Oblepias Dept: ISD Description: 1 prf have error and cannot proceed on interfacing from Portal to PRAS. | Setup Mistake | 2001680 is not setup in TIP_DEFAULT_VALUES | Setup the 2001680 in TIP_DEFAULT_VALUES. Note: If there is new cost center always check the setup also in TIP_DEFAULT_VALUES. (See the countermeasure on the above attached file.) | For Acknowledgement | RON EZREL DE VILLA | SHUNN NUELI MAGNO | 02-Dec-2021 07:49 | - | -
41 | IT-1221-0004 | 09-Dec-2021 06:37 | 120L0001 | SHUNN NUELI MAGNO | PRAS | FIN_GL ¦ GL SETUP ¦ PRS Invalid Selected Code Combination | BU: I. PONADO DEPT: FIA Encountered error "Invalid Selected Code in GL Code Combination Setup" upon applying for reimbursement in PRS System. | Setup Mistake | Code combination does not exist in PRAS (GL_CODE_COMBINATIONS). | Proceed with setup of code combination in GL Accounts then advise BU to retry transacting in PRS System to check if it becomes okay. (Kindy see "Countermeasure" sheet on the attached file above for detailed explanation). | Closed | - | SHUNN NUELI MAGNO | 10-Dec-2021 15:02 | SHUNN NUELI MAGNO | 10-Dec-2021 15:05
Number of record(s) : 41