## Issue Sheet
Issue Sheet | [17 empty] | Rev.1.0
r | Control Information
|  | Issue No. |  | TIP | I | A | 1465 | Type |  |  | Support |  | Status |  |  | OPEN
|  | Creation Date |  | 2018-12-20 |  |  |  | Due Date |  |  | 2018-12-20 |  | Close Date
|  | Priority |  | High |  |  |  | System |  |  | EBS |  | Application Module |  |  | MFG(Addon)
r | Inquiry Information
|  | [TIP ENDUSER/TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [ME-Sui]
|  |  | Request | Approval | [5 empty] | Registration |  | Approval |  |  | Reception |  | Assignment
|  | Dept. | ISD | HRD |  |  |  |  | Dept. |  |  |  |  | Dept.
|  | Name | R. De Villa | C.Tapia |  |  |  |  | Name |  |  |  |  | Name
|  | Date | 2018-12-20 | 2018-12-20 |  |  |  |  | Date |  |  |  |  | Date
|  | Issue Category |  | Operation
|  | Title |  | Development of AR Sales Report Generation
|  | Issue |  | Currently, AR sales interface report is generated daily thru PRAS <TIP OM Receivables User> system. FIA AR-in charge regularly received PRAS auto invoice notification every 5:00pm. PIC will proceed to check if interface import data are tallied versus invoice auto process data by using the given parameters (FTP File Name) in PRAS <TIP OM Receivables User>. If data are tallied consolidation of manual sales report will proceed. Therefore consolidation of monthly AR sales interface report will be completed after final daily interface.
|  | Reason |  | To create real-time AR sales report for the month and eliminate daily manual consolidation of AR sales Interface data
|  | Detail Attachment | [5 empty] | Link to Attachment Sheet
r | Investigation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Investigation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | ISD | HRD |  |  |  |  | Dept. |  |  |  |  | Dept.
|  | Name | R. De Villa | C.Tapia |  |  |  |  | Name |  |  |  |  | Name
|  | Date | 2018-12-20 | 2018-12-20 |  |  |  |  | Date |  |  |  |  | Date
Cause Category
|  | Cause |  | See detailed investigation result
Workaround and Countermeasure
|  | Detail Attachement | [5 empty] | Link to Attachment Sheet
r | Actual Operation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Operation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | [6 empty] | Dept. |  |  |  |  | Dept.
|  | Name | [6 empty] | Name |  |  |  |  | Name
|  | Date | [6 empty] | Date |  |  |  |  | Date
Actual Operation
|  | Evidence Attachment | [5 empty] | Link to Attachment Sheet
Note on C6: Control number 3 digits : Site short name (TIP) + 1 digit : Control classification (I : Issue) + 1 digit : Issued from (A : TIP-site, b : Japan-site) + 5 digits : Sequence number

## Datailed Inquiry Information
Detailed Inquiry Information

## Detailed Investigation Result
Detailed Investigation Result
SCRIPT
select
bt_cust.ACCOUNT_NAME BILL_TO_CUSTOMER,
--ra_int.ORIG_SYSTEM_BILL_CUSTOMER_ID BILL_TO_CUSTOMER,
st_cust.ACCOUNT_NAME SHIP_TO_CUSTOMER,
--ra_int.ORIG_SYSTEM_SHIP_CUSTOMER_ID SHIP_TO_CUSTOMER,
ra_int.TRX_NUMBER INVOICE_NUMBER,
ra_int.INTERFACE_LINE_ATTRIBUTE1 REF_NUMBER,
ra_int.INTERFACE_LINE_ATTRIBUTE2 REF_NUMBER2,
ra_int.TRX_DATE INVOICE_DATE,
pcg_sr_line.ITEM_NUMBER ITEM_CODE,
pcg_sr_line.ITEM_DESCRIPTION DESCRIPTION,
ra_int.CURRENCY_CODE CURRENCY,
ra_int.AMOUNT INVOICE_AMOUNT,
--Line Invoice Distribution
pcg_sr_line.SHIPPING_QUANTITY QUANTITY,
pcg_sr_line.UNIT_PRICE UNIT_STANDARD_PRICE,
pcg_sr_line.UNIT_PRICE*pcg_sr_line.SHIPPING_QUANTITY AMOUNT,
'' REMARKS,
ROWNUM RECORD_NUMBER,
-- Formatted field for display purpose
ra_int.AMOUNT FRMTD_INVOICE_AMOUNT,
pcg_sr_line.UNIT_PRICE FRMTD_UNIT_PRICE,
(pcg_sr_line.UNIT_PRICE*pcg_sr_line.SHIPPING_QUANTITY) FRMTD_AMOUNT,
stg_if.GL_DATE
from RA_INTERFACE_LINES_ALL ra_int,
XX00IFAR_TRX_HDR_IF_ALL stg_if,
HZ_CUST_ACCOUNTS st_cust,
HZ_CUST_ACCOUNTS bt_cust,
PCG_SR_LINES pcg_sr_line,
PCG_SA_INVOICE_LINES pcg_sa_line,
PCG_SA_INVOICE_HEADERS pcg_sa_hdr,
PCG_SR_HEADERS pcg_sr_hdr
where 1=1
and ra_int.interface_line_attribute1 = stg_if.interface_line_attribute1
--and ra_int.interface_line_attribute1 = 'H411-083067'
and ra_int.INTERFACE_LINE_ATTRIBUTE1 = pcg_sa_line.INVOICE_NUMBER
and pcg_sr_line.PO_NUMBER = pcg_sa_line.PO_NUMBER
and pcg_sa_line.INVOICE_NUMBER = pcg_sa_hdr.INVOICE_NUMBER
and pcg_sr_line.SR_LINE_NUMBER = pcg_sa_line.SR_SEQUENCE_NUMBER
and pcg_sr_hdr.SR_HEADER_ID = pcg_sr_line.SR_HEADER_ID
AND pcg_sa_line.SR_NUMBER = pcg_sr_hdr.SR_NUMBER
AND ra_int.attribute11 is not null
and st_cust.cust_account_id = ra_int.ORIG_SYSTEM_SHIP_CUSTOMER_ID
and bt_cust.cust_account_id = ra_int.ORIG_SYSTEM_BILL_CUSTOMER_ID
and stg_if.GL_DATE between '&GL_DATE1' and '&GL_DATE2'
UNION
SELECT bt_cust.ACCOUNT_NAME BILL_TO_CUSTOMER,
--ra_int.ORIG_SYSTEM_BILL_CUSTOMER_ID BILL_TO_CUSTOMER,
st_cust.ACCOUNT_NAME SHIP_TO_CUSTOMER,
--ra_int.ORIG_SYSTEM_SHIP_CUSTOMER_ID SHIP_TO_CUSTOMER,
ra_int.TRX_NUMBER INVOICE_NUMBER,
ra_int.INTERFACE_LINE_ATTRIBUTE1 REF_NUMBER,
ra_int.INTERFACE_LINE_ATTRIBUTE2 REF_NUMBER2,
ra_int.TRX_DATE INVOICE_DATE,
NULL ITEM_CODE,
ra_int.description DESCRIPTION,
ra_int.CURRENCY_CODE CURRENCY,
ra_int.AMOUNT INVOICE_AMOUNT,
--Line Invoice Distribution
1 QUANTITY,
1 UNIT_STANDARD_PRICE,
ra_int.AMOUNT AMOUNT,
'' REMARKS,
ROWNUM RECORD_NUMBER,
-- Formatted field for display purpose
ra_int.AMOUNT FRMTD_INVOICE_AMOUNT,
NULL FRMTD_UNIT_PRICE,
NULL FRMTD_AMOUNT,
stg_if.GL_DATE
FROM RA_INTERFACE_LINES_ALL ra_int,
XX00IFAR_TRX_HDR_IF_ALL stg_if,
HZ_CUST_ACCOUNTS bt_cust,
HZ_CUST_ACCOUNTS st_cust
where bt_cust.cust_account_id(+) = ra_int.ORIG_SYSTEM_BILL_CUSTOMER_ID
and st_cust.cust_account_id(+) = ra_int.ORIG_SYSTEM_SHIP_CUSTOMER_ID
and ra_int.interface_line_attribute1 = stg_if.interface_line_attribute1
AND ra_int.attribute11 is not null
and stg_if.GL_DATE between '&GL_DATE1' and '&GL_DATE2'
and (ra_int.INTERFACE_LINE_ATTRIBUTE1 LIKE '%CN%'
or ra_int.INTERFACE_LINE_ATTRIBUTE1 LIKE '%DN%'
--Add Start Lib_ver.4.03
or ra_int.INTERFACE_LINE_ATTRIBUTE1 LIKE '%BS%')
--Add End Lib_ver.4.03

## Actual Operation Evidence
Actual Operation Evidence

## Helpdesk Request
Helpdesk Request

## PP
Distribution : AP/SA - SV/M - SM - AP/SA (Keeping)
[5 empty] | Project Profile | [12 empty] | ISD.006.R0
Project ID |  |  | : | P18B0021 | [7 empty] | Reference No : |  | 2018-10-01073
Project name |  |  | : | Development of AR Sales Report Generation
Name of system |  |  | : | Oracle Add-on Program
Start date |  |  | : | 2018-12-05
Scheduled delivery date |  |  | : | 2018-12-21
|  |  |  | Name | [9 empty] | Date
Execution |  | PL | : | Ron Ezrel De Villa | [9 empty] | 2018-12-20
Review |  | PM | : | Chielo Tapia | [9 empty] | 2018-12-20
Approval |  | SM | : | Emmanuel Jacob | [9 empty] | 2018-12-20
Approval from client |  | Client | : | Rhenan Tapia | [9 empty] | 2018-12-20
Demand/Terms of agreement |  |  | : | To create new Datadownload in PRAS Problem: Oracle Alert: Currently, AR sales interface report is generated daily thru PRAS <TIP OM Receivables User> system. FIA AR-in charge regularly received PRAS auto invoice notification every 5:00pm. PIC will proceed to check if interface import data are tallied versus invoice auto process data by using the given parameters (FTP File Name) in PRAS <TIP OM Receivables User>. If data are tallied consolidation of manual sales report will proceed. Therefore consolidation of monthly AR sales interface report will be completed after final daily interface. Purpose: To create real-time AR sales report for the month and eliminate daily manual consolidation of AR sales Interface data
Impact Analysis/Scope of work |  |  | : | To remove daily manual consolidation of AR sales interface data
Development process / Quotation / Deliverables / Quality Assurance
Development contents |  |  | : | A. Software Development
B. Maintenance [ Bug / Trouble / Recovery / Others( )]
Stage | Development Process |  |  | Quotation | [6 empty] | Development |  | Quality assurance plan
|  |  |  | Man-hours （Man-days） |  | Scheduled completion date Actual performance |  |  | Program volume |  |  |  | Execution by AP/SA Date confirmed |  | Reviewer (SA/SV) Date confirmed | Approved by Mgr Date approved
User Requirement Definition | ○ |  |  | - |  | - |  |  | - |  | Requirement definition document |  | - |  | - | -
General plan | ○ |  |  | - |  | - |  |  | 1 |  | General plan |  | - |  | - | -
Detailed plan | ○ |  |  | 3 |  | 2018-12-05 |  |  |  |  | Detailed plan |  | 2018-12-07 |  | 2018-12-07 | 2018-12-07
Coding | ○ |  |  | 3 |  | 2018-12-12 |  |  |  |  | Source |  | 2018-12-14 |  | 2018-12-14 | 2018-12-14
Unit test | ○ |  |  | 1 |  | 2018-12-19 |  |  |  |  | Report of unit test result |  | 2018-12-19 |  | 2018-12-19 | 2018-12-19
Integration test | ○ |  |  | 1 |  | 2018-12-20 |  |  |  |  | Report of integration test result |  | 2018-12-20 |  | 2018-12-20 | 2018-12-20
↑Enter page number if document
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | ソースファイル名 | [8 empty] | テスト仕様書兼単体テストドキュメント
Confirmation of Applying to Production
Releasing date confirmation |  |  | : | 2018-12-21 |  |  |  |  | Ron Ezrel De Villa
System check-in confirmation |  |  | : | 2018-12-21 |  |  |  |  | Maria Chielo Tapia
Release approval (ISD) |  |  | : | 2018-12-21 |  |  |  |  | Emmanuel Jacob
Release approval （Client） |  |  | : | 2018-12-21 |  |  |  |  | Rhenan Tapia
Applied to Production by |  |  | : | 2018-12-21
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | チェックイン先 | [8 empty] | 本番適用
Confirmation of Completion
Acceptance |  | (Internal) |  | 2018-12-21 |  |  |  | ISD |  |  |  | Ron Ezrel De Villa
|  | (External) |  | 2018-12-21 |  |  |  | ISD |  |  |  | Rhenan Tapia |  |  |  |  | (Client)

## Project Profile (hidden)
Distribution : AP/SA - SV/M - SM - AP/SA (Keeping)
[5 empty] | Project Profile | [11 empty] | ISD.006.R0
Project ID |  |  | : | [7 empty] | Reference No :
Project name |  |  | :
Name of system |  |  | :
Start date |  |  | :
Scheduled delivery date |  |  | :
|  |  |  | Name | [8 empty] | Date
Execution |  | PL | :
Review |  | PM | :
Approval |  | SM | :
Approval from client |  | Client | :
Demand/Terms of agreement |  |  | :
Impact Analysis/Scope of work |  |  | :
Development process / Quotation / Deliverables / Quality Assurance
Development contents |  |  | : | A. Software Development
B. Maintenance [ Bug / Trouble / Recovery / Others( )]
Stage | Development Process |  |  | Quotation | [5 empty] | Development |  | Quality assurance plan
|  |  |  | Man-hours （Man-days） |  | Scheduled completion date Actual performance |  | Program volume |  |  |  | Execution by AP/SA Date confirmed |  | Reviewer (SA/SV) Date confirmed | Approved by Mgr Date approved
User Requirement Definition
General plan
Detailed plan
Coding
Unit test
Integration test
↑Enter page number if document
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | ソースファイル名 | [7 empty] | テスト仕様書兼単体テストドキュメント
Confirmation of Applying to Production
Releasing date confirmation |  |  | :
System check-in confirmation |  |  | :
Release approval (ISD) |  |  | :
Release approval （Client） |  |  | :
Applied to Production by |  |  | :
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | チェックイン先 | [7 empty] | 本番適用
Confirmation of Completion
Acceptance |  | (Internal)
|  | (External) | [13 empty] | (Client)
Note on L4: IS Project Issuing Number
Note on AH4: IS Helpdesk Control Number
Note on L7: > start of program modification/development or setup via backend (test environment) *same date with 'Coding' [row37; columns O~S and columns AD~AH] > setup via application - start of setup in test environment *'Coding' [row37; columns O~S] should be set to null
Note on L8: agreement between Client and TIP IS/ME SUI
Note on L10: AP (Analyst Programmer) / SA (System Analyst)
Note on AH10: Test Execution *actual exec date (can be multi/single date) *same date with 'Unit or Integration Test' [row38 or 39; columns O~S and AD~AH] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L11: SV (Supervisor) / M (Manager)
Note on AH11: Test Review *Review date (can be multi/single date) *same date with 'Unit or Integration Test' [rows 37, 38 or 39; columns AI~AM] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L12: M (Manager) / VP (Vice President)
Note on AH12: Test Approval *approval date(single date) *same date with 'Unit or Integration Test' [row 37, 38 or 39; columns AN~AR] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L13: BU (Business Unit)
Note on AH13: Test Approval *approval date *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on I34: [o] *required [-] *not required
Note on L34: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O34: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T34: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN34: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I35: [o] *required [-] *not required
Note on L35: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O35: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T35: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN35: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I36: [o] *required [-] *not required
Note on L36: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O36: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T36: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN36: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I37: [o] *required [-] *not required
Note on L37: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O37: -if Dev't Process is [o], indicate the actual performace date *same date with 'Start date' [row7; columns L~T] *not applicable in: 'setup via application' -if Dev't Process is [-], set to [-]
Note on T37: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Start date' [row7; columns L~T] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AI37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AN37: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on I38: [o] *required [-] *not required
Note on L38: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O38: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T38: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD38: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI38: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN38: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on I39: [o] *required [-] *not required
Note on L39: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O39: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T39: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on W39: Enter implemented user test item.
Note on AD39: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI39: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN39: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on L51: Target Envi: Production *same date with Migration Request's 'Applicant' request date [row9; column E]
Note on T51: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on L52: Target Envi: Production *same date with Migration Request's 'Approved' date [row9; column F]
Note on T52: SV (Supervisor) / M (Manager) -> PM (Project Manager)
Note on L53: Target Envi: Production *same date with Migration Request's 'Manager' approved date [row9; column G]
Note on T53: M (Manager) / VP (Vice President) -> SM (Senior Project Manager)
Note on L54: Target Envi: Production *same date with Migration Request's 'Date for Migration' date [row35; columns D~E]
Note on T54: BU (Business Unit) -> Client
Note on L55: Target Envi: Production *same date with Migration Request's 'Actual Date of Migration' date [row36; columns D~E and row39; column D]
Note on T55: ME Sui Librarian
Note on L66: date confirmation after Prod implem
Note on S66: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on AC66: Dep't/Div
Note on L67: date confirmation after Prod implem
Note on S67: BU (Business Unit) -> Client
Note on AC67: Dep't/Div

## Migration Request (hidden)
ISD.005.R2
Project No.
J-SOX Request No.
Migration Request |  | Applicant | Approved by | Manager
Date of application
Programs to migrate | Program Name |  | Directory
Production library name
Date of Receipt
Date for Migration
Actual Date of Migration
| Librarian | Manager | Reviewer | Log Reviewer
Note on F5: based on TIP-ISD's Project Issuing #
Note on F6: based on ME-SUI's's J-SOX System Issuing #
Note on E9: -same with Project Profile's 'AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)' [row51; columns T~AR] and 'Releasing date confirmation' [row51; columns L~R] - <name> - <date>
Note on F9: -same with Project Profile's 'SV (Supervisor) / M (Manager) -> PM (Project Manager)' [row52; columns T~AR] and 'System check-in confirmationn' [row52; columns L~R] - <name> - <date>
Note on G9: -same with Project Profile's 'M (Manager) / VP (Vice President) -> SM (Senior Project Manager)' [row53; columns T~AR] and 'Release approval (ISD)' [row53; columns L~R] - <name> - <date>
Note on D34: request receiving date
Note on D35: same date with Project Profile's 'Release approval (Client)' date (row54; columns L~R)
Note on D36: same date with Project Profile's 'Applied to Production' date (row55; colums L~R)
Note on D39: same with Project Profile's 'Applied to Production by' - ME-Sui Librarian [row55; columns T~AR] and date [row55; columns L~R] - <name> - <date>
Note on E39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>
Note on G39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>