## Issue Sheet
Issue Sheet | [17 empty] | Rev.1.0
r | Control Information
|  | Issue No. |  | TIP | I | A | 2088 | Type |  |  | Request |  | Status |  |  | OPEN
|  | Creation Date |  | 2021-08-25 |  |  |  | Due Date |  |  | 2021-08-25 |  | Close Date
|  | Priority |  | High |  |  |  | System |  |  | EBS |  | Application Module |  |  | MFG(Addon)
r | Inquiry Information
|  | [TIP ENDUSER/TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [ME-Sui]
|  |  | Request | Approval | [5 empty] | Registration |  | Approval |  |  | Reception |  | Assignment
|  | Dept. | TIP-ISD | TIP-ISD |  |  |  |  | Dept. |  |  |  |  | Dept.
|  | Name | R. De Villa | E. Jacob |  |  |  |  | Name |  |  |  |  | Name
|  | Date | 2021-08-25 | 2021-08-25 |  |  |  |  | Date |  |  |  |  | Date
|  | Issue Category |  | Operation
|  | Title |  | Request for OCI GAIA Upper System config file update
|  | Issue |  | .dat file from Pras Financials wasn't able to interface to GAIA after the OCA GAIA Server Migration
|  | Reason |  | missed to change our configuration files to gftp.gaia.toshiba.co.jp (ESB).
|  | Detail Attachment | [5 empty] | Link to Attachment Sheet
r | Investigation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Investigation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | TIP-ISD | TIP-ISD |  |  |  |  | Dept. |  |  |  |  | Dept.
|  | Name | R. De Villa | E. Jacob |  |  |  |  | Name |  |  |  |  | Name
|  | Date | 2021-08-25 | 2021-08-25 |  |  |  |  | Date |  |  |  |  | Date
|  | Cause Category |  | Operation Mistake
|  | Cause |  | missed to change our configuration files to gftp.gaia.toshiba.co.jp (ESB). Config files was change after the server migration
Workaround and Countermeasure
|  | Detail Attachement | [5 empty] | Link to Attachment Sheet
r | Actual Operation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Operation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | [6 empty] | Dept. |  |  |  |  | Dept.
|  | Name | [6 empty] | Name |  |  |  |  | Name
|  | Date | [6 empty] | Date |  |  |  |  | Date
Actual Operation
|  | Evidence Attachment | [5 empty] | Link to Attachment Sheet
Note on C6: Control number 3 digits : Site short name (TIP) + 1 digit : Control classification (I : Issue) + 1 digit : Issued from (A : TIP-site, b : Japan-site) + 5 digits : Sequence number

## Detailed Investigation Result
Detailed Investigation Result
| SOURCE_CODE | ORGANIZATION_CODE | ORGANIZATION_ID | ASSEMBLY_CODE | ASSEMBLY_ID | CLASS_CODE | JOB_NAME | QUANTITY | COMPLETION_DATE | ALTERNATE_ROUTING_DESIGNATOR | ALTERNATE_BOM_DESIGNATOR | ATTRIBUTE1 | ATTRIBUTE2 | ATTRIBUTE3 | ATTRIBUTE4 | ATTRIBUTE5 | ATTRIBUTE6 | ATTRIBUTE7 | ATTRIBUTE8 | ATTRIBUTE9 | ATTRIBUTE10 | CREATION_DATE | UPDATE_DATE | PROCESS_FLAG | ERROR_MESSAGE
| SOURCE_CODE | ORGANIZATION_CODE | ORGANIZATION_ID | ASSEMBLY_CODE | ASSEMBLY_ID | CLASS_CODE | JOB_NAME | QUANTITY | COMPLETION_DATE | ALTERNATE_ROUTING_DESIGNATOR | ALTERNATE_BOM_DESIGNATOR | ATTRIBUTE1 | ATTRIBUTE2 | ATTRIBUTE3 | ATTRIBUTE4 | ATTRIBUTE5 | ATTRIBUTE6 | ATTRIBUTE7 | ATTRIBUTE8 | ATTRIBUTE9 | ATTRIBUTE10 | CREATION_DATE | UPDATE_DATE | PROCESS_FLAG | ERROR_MESSAGE
| TIPWIPS020 | ESD | 125 | SDFUS86DAB01TG0T | 3757005 | Standard | ESD00298151 | 210 | 2021-06-29 14:42 | MPL | MPL | ESDLINE | [9 empty] | 2021-06-29 14:42 | 2021-06-29 14:43 | 9 | No operation sequence found for (ESD00298151).
| TIPWIPS020 | ESD | 125 | SDFSU83GEB02T80T | 3709748 | Standard | ESD00298152 | 60 | 2021-06-29 14:42 | MPL | MPL | ESDLINE | [9 empty] | 2021-06-29 14:42 | 2021-06-29 14:43 | 9 | No operation sequence found for (ESD00298152).
| TIPWIPS020 | ESD | 125 | SDFUS85DAB01TE0T | 3757003 | Standard | ESD00298153 | 90 | 2021-06-29 14:42 | MPL | MPL | ESDLINE | [9 empty] | 2021-06-29 14:42 | 2021-06-29 14:43 | 9 | No operation sequence found for (ESD00298153).
| TIPWIPS020 | ESD | 125 | SDFUS84DAB01TC0T | 3756997 | Standard | ESD00298154 | 180 | 2021-06-29 14:42 | MPL | MPL | ESDLINE | [9 empty] | 2021-06-29 14:42 | 2021-06-29 14:43 | 9 | No operation sequence found for (ESD00298154).
SELECT WO.*
FROM WIP_OPERATIONS WO,
WIP_ENTITIES WE
WHERE WO.WIP_ENTITY_ID = WE.WIP_ENTITY_ID
AND WE.WIP_ENTITY_NAME IN (SELECT job_name
FROM TIP_SSDMO_INTERFACE
WHERE process_flag = '9')
AND WO.NEXT_OPERATION_SEQ_NUM IS NULL;
WIP_OPERATIONS
| WIP_ENTITY_ID | OPERATION_SEQ_NUM | ORGANIZATION_ID | REPETITIVE_SCHEDULE_ID | LAST_UPDATE_DATE | LAST_UPDATED_BY | CREATION_DATE | CREATED_BY | LAST_UPDATE_LOGIN | REQUEST_ID | PROGRAM_APPLICATION_ID | PROGRAM_ID | PROGRAM_UPDATE_DATE | OPERATION_SEQUENCE_ID | STANDARD_OPERATION_ID | DEPARTMENT_ID | DESCRIPTION | SCHEDULED_QUANTITY | QUANTITY_IN_QUEUE | QUANTITY_RUNNING | QUANTITY_WAITING_TO_MOVE | QUANTITY_REJECTED | QUANTITY_SCRAPPED | QUANTITY_COMPLETED | FIRST_UNIT_START_DATE | FIRST_UNIT_COMPLETION_DATE | LAST_UNIT_START_DATE | LAST_UNIT_COMPLETION_DATE | PREVIOUS_OPERATION_SEQ_NUM | NEXT_OPERATION_SEQ_NUM | COUNT_POINT_TYPE | BACKFLUSH_FLAG | MINIMUM_TRANSFER_QUANTITY | DATE_LAST_MOVED | ATTRIBUTE_CATEGORY | ATTRIBUTE1 | ATTRIBUTE2 | ATTRIBUTE3 | ATTRIBUTE4 | ATTRIBUTE5 | ATTRIBUTE6 | ATTRIBUTE7 | ATTRIBUTE8 | ATTRIBUTE9 | ATTRIBUTE10 | ATTRIBUTE11 | ATTRIBUTE12 | ATTRIBUTE13 | ATTRIBUTE14 | ATTRIBUTE15 | WF_ITEMTYPE | WF_ITEMKEY | OPERATION_YIELD | OPERATION_YIELD_ENABLED | PRE_SPLIT_QUANTITY | OPERATION_COMPLETED | SHUTDOWN_TYPE | X_POS | Y_POS | PREVIOUS_OPERATION_SEQ_ID | SKIP_FLAG | LONG_DESCRIPTION | CUMULATIVE_SCRAP_QUANTITY | DISABLE_DATE | RECOMMENDED | PROGRESS_PERCENTAGE | WSM_OP_SEQ_NUM | WSM_BONUS_QUANTITY | EMPLOYEE_ID | ACTUAL_START_DATE | ACTUAL_COMPLETION_DATE | PROJECTED_COMPLETION_DATE | WSM_UPDATE_QUANTITY_TXN_ID | WSM_COSTED_QUANTITY_COMPLETED | LOWEST_ACCEPTABLE_YIELD | CHECK_SKILL
| 12201761 | 10 | 125 |  | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 | 47385415 | 45995209 | 706 | 35740 | 2021-06-29 14:43 | 3097357 |  | 3 |  | 210 | 210 | 0 | 0 | 0 | 0 | 0 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 |  |  | 1 | 1 | 0 | [29 empty] | 0 | [12 empty] | 2
| 12201762 | 10 | 125 |  | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 | 47385415 | 45995209 | 706 | 35740 | 2021-06-29 14:43 | 3057849 |  | 3 |  | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 |  |  | 1 | 1 | 0 | [29 empty] | 0 | [12 empty] | 2
| 12201763 | 10 | 125 |  | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 | 47385415 | 45995209 | 706 | 35740 | 2021-06-29 14:43 | 3097355 |  | 3 |  | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 |  |  | 1 | 1 | 0 | [29 empty] | 0 | [12 empty] | 2
| 12201764 | 10 | 125 |  | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 | 47385415 | 45995209 | 706 | 35740 | 2021-06-29 14:43 | 3097353 |  | 3 |  | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 | 2021-06-29 14:42 |  |  | 1 | 1 | 0 | [29 empty] | 0 | [12 empty] | 2
SELECT WE.*
FROM WIP_OPERATIONS WO,
WIP_ENTITIES WE
WHERE WO.WIP_ENTITY_ID = WE.WIP_ENTITY_ID
AND WE.WIP_ENTITY_NAME IN (SELECT job_name
FROM TIP_SSDMO_INTERFACE
WHERE process_flag = '9')
AND WO.NEXT_OPERATION_SEQ_NUM IS NULL;
WIP_ENTITIES
| WIP_ENTITY_ID | ORGANIZATION_ID | LAST_UPDATE_DATE | LAST_UPDATED_BY | CREATION_DATE | CREATED_BY | LAST_UPDATE_LOGIN | REQUEST_ID | PROGRAM_APPLICATION_ID | PROGRAM_ID | PROGRAM_UPDATE_DATE | WIP_ENTITY_NAME | ENTITY_TYPE | DESCRIPTION | PRIMARY_ITEM_ID | GEN_OBJECT_ID
| WIP_ENTITY_ID | ORGANIZATION_ID | LAST_UPDATE_DATE | LAST_UPDATED_BY | CREATION_DATE | CREATED_BY | LAST_UPDATE_LOGIN | REQUEST_ID | PROGRAM_APPLICATION_ID | PROGRAM_ID | PROGRAM_UPDATE_DATE | WIP_ENTITY_NAME | ENTITY_TYPE | DESCRIPTION | PRIMARY_ITEM_ID | GEN_OBJECT_ID
| 12201761 | 125 | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 |  | 45995209 | 706 | 35740 | 2021-06-29 14:43 | ESD00298151 | 1 | Job Mass Loaded on 29-JUN-2021 14:42:31 (server timezone) | 3757005 | 14824959
| 12201762 | 125 | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 |  | 45995209 | 706 | 35740 | 2021-06-29 14:43 | ESD00298152 | 1 | Job Mass Loaded on 29-JUN-2021 14:42:31 (server timezone) | 3709748 | 14824960
| 12201763 | 125 | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 |  | 45995209 | 706 | 35740 | 2021-06-29 14:43 | ESD00298153 | 1 | Job Mass Loaded on 29-JUN-2021 14:42:31 (server timezone) | 3757003 | 14824961
| 12201764 | 125 | 2021-06-29 14:43 | 4862 | 2021-06-29 14:43 | 4862 |  | 45995209 | 706 | 35740 | 2021-06-29 14:43 | ESD00298154 | 1 | Job Mass Loaded on 29-JUN-2021 14:42:31 (server timezone) | 3756997 | 14824962

## Actual Operation Evidence
Actual Operation Evidence
SELECT *
FROM APPS.TIP_SSDMO_INTERFACE
WHERE process_flag = '9'
AND organization_code = 'ESD'
AND job_name IN ('ESD00298151','ESD00298152','ESD00298153','ESD00298154');
| SOURCE_CODE | ORGANIZATION_CODE | ORGANIZATION_ID | ASSEMBLY_CODE | ASSEMBLY_ID | CLASS_CODE | JOB_NAME | QUANTITY | COMPLETION_DATE | ALTERNATE_ROUTING_DESIGNATOR | ALTERNATE_BOM_DESIGNATOR | ATTRIBUTE1 | ATTRIBUTE2 | ATTRIBUTE3 | ATTRIBUTE4 | ATTRIBUTE5 | ATTRIBUTE6 | ATTRIBUTE7 | ATTRIBUTE8 | ATTRIBUTE9 | ATTRIBUTE10 | CREATION_DATE | UPDATE_DATE | PROCESS_FLAG | ERROR_MESSAGE
| TIPWIPS020 | ESD | 125 | SDFUS86DAB01TG0T | 3757005 | Standard | ESD00298151 | 210 | 6/29/2021 2:42:18 PM | MPL | MPL | ESDLINE | [9 empty] | 6/29/2021 2:42:18 PM | 6/29/2021 2:42:44 PM | 9 | No operation sequence found for (ESD00298151).
| TIPWIPS020 | ESD | 125 | SDFSU83GEB02T80T | 3709748 | Standard | ESD00298152 | 60 | 6/29/2021 2:42:20 PM | MPL | MPL | ESDLINE | [9 empty] | 6/29/2021 2:42:20 PM | 6/29/2021 2:42:44 PM | 9 | No operation sequence found for (ESD00298152).
| TIPWIPS020 | ESD | 125 | SDFUS85DAB01TE0T | 3757003 | Standard | ESD00298153 | 90 | 6/29/2021 2:42:20 PM | MPL | MPL | ESDLINE | [9 empty] | 6/29/2021 2:42:20 PM | 6/29/2021 2:42:44 PM | 9 | No operation sequence found for (ESD00298153).
| TIPWIPS020 | ESD | 125 | SDFUS84DAB01TC0T | 3756997 | Standard | ESD00298154 | 180 | 6/29/2021 2:42:21 PM | MPL | MPL | ESDLINE | [9 empty] | 6/29/2021 2:42:21 PM | 6/29/2021 2:42:44 PM | 9 | No operation sequence found for (ESD00298154).

## Helpdesk Request
Helpdesk Request
ATTACH SCREENSHOT OF HELPDESK REQUEST.

## Project Profile (hidden)
Distribution : AP/SA - SV/M - SM - AP/SA (Keeping)
[5 empty] | Project Profile | [11 empty] | ISD.006.R0
Project ID |  |  | : | [7 empty] | Reference No :
Project name |  |  | :
Name of system |  |  | :
Start date |  |  | :
Scheduled delivery date |  |  | :
|  |  |  | Name | [8 empty] | Date
Execution |  | PL | :
Review |  | PM | :
Approval |  | SM | :
Approval from client |  | Client | :
Demand/Terms of agreement |  |  | :
Impact Analysis/Scope of work |  |  | :
Development process / Quotation / Deliverables / Quality Assurance
Development contents |  |  | : | A. Software Development
B. Maintenance [ Bug / Trouble / Recovery / Others( )]
Stage | Development Process |  |  | Quotation | [5 empty] | Development |  | Quality assurance plan
|  |  |  | Man-hours （Man-days） |  | Scheduled completion date Actual performance |  | Program volume |  |  |  | Execution by AP/SA Date confirmed |  | Reviewer (SA/SV) Date confirmed | Approved by Mgr Date approved
User Requirement Definition
General plan
Detailed plan
Coding
Unit test
Integration test
↑Enter page number if document
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | ソースファイル名 | [7 empty] | テスト仕様書兼単体テストドキュメント
Confirmation of Applying to Production
Releasing date confirmation |  |  | :
System check-in confirmation |  |  | :
Release approval (ISD) |  |  | :
Release approval （Client） |  |  | :
Applied to Production by |  |  | :
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | チェックイン先 | [7 empty] | 本番適用
Confirmation of Completion
Acceptance |  | (Internal)
|  | (External) | [13 empty] | (Client)
Note on L4: IS Project Issuing Number
Note on AH4: IS Helpdesk Control Number
Note on L7: > start of program modification/development or setup via backend (test environment) *same date with 'Coding' [row37; columns O~S and columns AD~AH] > setup via application - start of setup in test environment *'Coding' [row37; columns O~S] should be set to null
Note on L8: agreement between Client and TIP IS/ME SUI
Note on L10: AP (Analyst Programmer) / SA (System Analyst)
Note on AH10: Test Execution *actual exec date (can be multi/single date) *same date with 'Unit or Integration Test' [row38 or 39; columns O~S and AD~AH] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L11: SV (Supervisor) / M (Manager)
Note on AH11: Test Review *Review date (can be multi/single date) *same date with 'Unit or Integration Test' [rows 37, 38 or 39; columns AI~AM] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L12: M (Manager) / VP (Vice President)
Note on AH12: Test Approval *approval date(single date) *same date with 'Unit or Integration Test' [row 37, 38 or 39; columns AN~AR] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L13: BU (Business Unit)
Note on AH13: Test Approval *approval date *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on I34: [o] *required [-] *not required
Note on L34: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O34: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T34: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN34: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I35: [o] *required [-] *not required
Note on L35: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O35: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T35: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN35: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I36: [o] *required [-] *not required
Note on L36: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O36: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T36: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN36: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I37: [o] *required [-] *not required
Note on L37: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O37: -if Dev't Process is [o], indicate the actual performace date *same date with 'Start date' [row7; columns L~T] *not applicable in: 'setup via application' -if Dev't Process is [-], set to [-]
Note on T37: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Start date' [row7; columns L~T] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AI37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AN37: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on I38: [o] *required [-] *not required
Note on L38: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O38: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T38: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD38: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI38: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN38: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on I39: [o] *required [-] *not required
Note on L39: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O39: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T39: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on W39: Enter implemented user test item.
Note on AD39: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI39: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN39: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on L51: Target Envi: Production *same date with Migration Request's 'Applicant' request date [row9; column E]
Note on T51: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on L52: Target Envi: Production *same date with Migration Request's 'Approved' date [row9; column F]
Note on T52: SV (Supervisor) / M (Manager) -> PM (Project Manager)
Note on L53: Target Envi: Production *same date with Migration Request's 'Manager' approved date [row9; column G]
Note on T53: M (Manager) / VP (Vice President) -> SM (Senior Project Manager)
Note on L54: Target Envi: Production *same date with Migration Request's 'Date for Migration' date [row35; columns D~E]
Note on T54: BU (Business Unit) -> Client
Note on L55: Target Envi: Production *same date with Migration Request's 'Actual Date of Migration' date [row36; columns D~E and row39; column D]
Note on T55: ME Sui Librarian
Note on L66: date confirmation after Prod implem
Note on S66: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on AC66: Dep't/Div
Note on L67: date confirmation after Prod implem
Note on S67: BU (Business Unit) -> Client
Note on AC67: Dep't/Div

## Migration Request (hidden)
ISD.005.R2
Project No.
J-SOX Request No.
Migration Request |  | Applicant | Approved by | Manager
Date of application
Programs to migrate | Program Name |  | Directory
Production library name
Date of Receipt
Date for Migration
Actual Date of Migration
| Librarian | Manager | Reviewer | Log Reviewer
Note on F5: based on TIP-ISD's Project Issuing #
Note on F6: based on ME-SUI's's J-SOX System Issuing #
Note on E9: -same with Project Profile's 'AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)' [row51; columns T~AR] and 'Releasing date confirmation' [row51; columns L~R] - <name> - <date>
Note on F9: -same with Project Profile's 'SV (Supervisor) / M (Manager) -> PM (Project Manager)' [row52; columns T~AR] and 'System check-in confirmationn' [row52; columns L~R] - <name> - <date>
Note on G9: -same with Project Profile's 'M (Manager) / VP (Vice President) -> SM (Senior Project Manager)' [row53; columns T~AR] and 'Release approval (ISD)' [row53; columns L~R] - <name> - <date>
Note on D34: request receiving date
Note on D35: same date with Project Profile's 'Release approval (Client)' date (row54; columns L~R)
Note on D36: same date with Project Profile's 'Applied to Production' date (row55; colums L~R)
Note on D39: same with Project Profile's 'Applied to Production by' - ME-Sui Librarian [row55; columns T~AR] and date [row55; columns L~R] - <name> - <date>
Note on E39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>
Note on G39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>