## Issue Sheet
Issue Sheet | [17 empty] | Rev.1.0
r | Control Information
|  | Issue No. |  | TIP | I | A | 2079 | Type |  |  | Request |  | Status |  |  | OPEN
|  | Creation Date |  | 2021-08-05 |  |  |  | Due Date |  |  | 2021-08-05 |  | Close Date
|  | Priority |  | High |  |  |  | System |  |  | EBS |  | Application Module |  |  | Common
r | Inquiry Information
|  | [TIP ENDUSER/TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [ME-Sui]
|  |  | Request | Approval | [5 empty] | Registration |  | Approval |  |  | Reception |  | Assignment
|  | Dept. | TIP-ISD | TIP-ISD |  |  |  |  | Dept. |  |  |  |  | Dept.
|  | Name | R. De Villa | E. Jacob |  |  |  |  | Name |  |  |  |  | Name
|  | Date | 2021-08-05 | 2021-08-05 |  |  |  |  | Date |  |  |  |  | Date
|  | Issue Category |  | Operation
|  | Title |  | Modification of OPE Code Shipment control for eSSD
|  | Issue |  | AS part of shipment control improvement, OPE code assignment will be implemented in ESSD. 1. OPE CODE will be added in SI Data in Ocean System 2. OPE CODE Data needs to be add in FG Dat on PRAS System for Shipment Control
Reason
|  | Detail Attachment | [5 empty] | Link to Attachment Sheet
r | Investigation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Investigation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | [6 empty] | Dept. |  |  |  |  | Dept.
|  | Name | [6 empty] | Name |  |  |  |  | Name
|  | Date | [6 empty] | Date |  |  |  |  | Date
Cause Category
Cause
Workaround and Countermeasure
|  | Detail Attachement | [5 empty] | Link to Attachment Sheet
r | Actual Operation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Operation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | [6 empty] | Dept. |  |  |  |  | Dept.
|  | Name | [6 empty] | Name |  |  |  |  | Name
|  | Date | [6 empty] | Date |  |  |  |  | Date
Actual Operation
|  | Evidence Attachment | [5 empty] | Link to Attachment Sheet
Note on C6: Control number 3 digits : Site short name (TIP) + 1 digit : Control classification (I : Issue) + 1 digit : Issued from (A : TIP-site, b : Japan-site) + 5 digits : Sequence number

## Detailed Investigation Result
Detailed Investigation Result
Modify Program XXOMS0607 Import ASN Serial Information for eSSD
Add PCM_DEFAULT_VALUES parameter for eSSD
PCM_DEFAULT_VALUES
| ORGANIZATION_ID | TABLE_NAME | FIELD_NAME | ADDITIONAL_KEY | DEFAULT_VALUE | OWNER | DESCRIPTION | CREATED_BY | CREATION_DATE | LAST_UPDATED_BY | LAST_UPDATE_DATE
| 102 | INVF0031 | OPE_CODE_ORG | 1 | EHD | XXOM | for INVF0031/INVF0032 | -1 | 2015-03-31 | -1 | 2015-03-31 | for EHD
| 132 | PCGS5030 | ORGANIZATION_CODE | GET_OPE_CODE | EHD | XXOM | for PCGS5030 | -1 | 2015-03-31 | -1 | 2015-03-31 | for EHD
| 132 | PCGS5100 | ORGANIZATION_CODE | GET_OPE_CODE | EHD | XXOM | for PCGS5100 | -1 | 2015-03-31 | -1 | 2015-03-31 | for EHD
| 102 | INVF0031 | OPE_CODE_ORG | 2 | ESD | XXOM | for INVF0031/INVF0032 | -1 | 2021-08-10 | -1 | 2021-08-10 | for ESD
| 125 | PCGS5030 | ORGANIZATION_CODE | GET_OPE_CODE | ESD | XXOM | for PCGS5030 | -1 | 2021-08-10 | -1 | 2021-08-10 | for ESD
| 125 | PCGS5100 | ORGANIZATION_CODE | GET_OPE_CODE | ESD | XXOM | for PCGS5100 | -1 | 2021-08-10 | -1 | 2021-08-10 | for ESD
Packing system add
HDM_IDS_ASN_SERIAL18_V.OPE_CODE column
change connect column
from null
to HDM_IDS_ASN_SERIAL18_V.OPE_CODE

## Actual Operation Evidence
Actual Operation Evidence

## Helpdesk Request
Helpdesk Request
ATTACH SCREENSHOT OF HELPDESK REQUEST.

## Project Profile (hidden)
Distribution : AP/SA - SV/M - SM - AP/SA (Keeping)
[5 empty] | Project Profile | [11 empty] | ISD.006.R0
Project ID |  |  | : | [7 empty] | Reference No :
Project name |  |  | :
Name of system |  |  | :
Start date |  |  | :
Scheduled delivery date |  |  | :
|  |  |  | Name | [8 empty] | Date
Execution |  | PL | :
Review |  | PM | :
Approval |  | SM | :
Approval from client |  | Client | :
Demand/Terms of agreement |  |  | :
Impact Analysis/Scope of work |  |  | :
Development process / Quotation / Deliverables / Quality Assurance
Development contents |  |  | : | A. Software Development
B. Maintenance [ Bug / Trouble / Recovery / Others( )]
Stage | Development Process |  |  | Quotation | [5 empty] | Development |  | Quality assurance plan
|  |  |  | Man-hours （Man-days） |  | Scheduled completion date Actual performance |  | Program volume |  |  |  | Execution by AP/SA Date confirmed |  | Reviewer (SA/SV) Date confirmed | Approved by Mgr Date approved
User Requirement Definition
General plan
Detailed plan
Coding
Unit test
Integration test
↑Enter page number if document
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | ソースファイル名 | [7 empty] | テスト仕様書兼単体テストドキュメント
Confirmation of Applying to Production
Releasing date confirmation |  |  | :
System check-in confirmation |  |  | :
Release approval (ISD) |  |  | :
Release approval （Client） |  |  | :
Applied to Production by |  |  | :
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | チェックイン先 | [7 empty] | 本番適用
Confirmation of Completion
Acceptance |  | (Internal)
|  | (External) | [13 empty] | (Client)
Note on L4: IS Project Issuing Number
Note on AH4: IS Helpdesk Control Number
Note on L7: > start of program modification/development or setup via backend (test environment) *same date with 'Coding' [row37; columns O~S and columns AD~AH] > setup via application - start of setup in test environment *'Coding' [row37; columns O~S] should be set to null
Note on L8: agreement between Client and TIP IS/ME SUI
Note on L10: AP (Analyst Programmer) / SA (System Analyst)
Note on AH10: Test Execution *actual exec date (can be multi/single date) *same date with 'Unit or Integration Test' [row38 or 39; columns O~S and AD~AH] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L11: SV (Supervisor) / M (Manager)
Note on AH11: Test Review *Review date (can be multi/single date) *same date with 'Unit or Integration Test' [rows 37, 38 or 39; columns AI~AM] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L12: M (Manager) / VP (Vice President)
Note on AH12: Test Approval *approval date(single date) *same date with 'Unit or Integration Test' [row 37, 38 or 39; columns AN~AR] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L13: BU (Business Unit)
Note on AH13: Test Approval *approval date *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on I34: [o] *required [-] *not required
Note on L34: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O34: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T34: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN34: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I35: [o] *required [-] *not required
Note on L35: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O35: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T35: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN35: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I36: [o] *required [-] *not required
Note on L36: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O36: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T36: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN36: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I37: [o] *required [-] *not required
Note on L37: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O37: -if Dev't Process is [o], indicate the actual performace date *same date with 'Start date' [row7; columns L~T] *not applicable in: 'setup via application' -if Dev't Process is [-], set to [-]
Note on T37: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Start date' [row7; columns L~T] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AI37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AN37: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on I38: [o] *required [-] *not required
Note on L38: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O38: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T38: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD38: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI38: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN38: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on I39: [o] *required [-] *not required
Note on L39: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O39: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T39: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on W39: Enter implemented user test item.
Note on AD39: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI39: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN39: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on L51: Target Envi: Production *same date with Migration Request's 'Applicant' request date [row9; column E]
Note on T51: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on L52: Target Envi: Production *same date with Migration Request's 'Approved' date [row9; column F]
Note on T52: SV (Supervisor) / M (Manager) -> PM (Project Manager)
Note on L53: Target Envi: Production *same date with Migration Request's 'Manager' approved date [row9; column G]
Note on T53: M (Manager) / VP (Vice President) -> SM (Senior Project Manager)
Note on L54: Target Envi: Production *same date with Migration Request's 'Date for Migration' date [row35; columns D~E]
Note on T54: BU (Business Unit) -> Client
Note on L55: Target Envi: Production *same date with Migration Request's 'Actual Date of Migration' date [row36; columns D~E and row39; column D]
Note on T55: ME Sui Librarian
Note on L66: date confirmation after Prod implem
Note on S66: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on AC66: Dep't/Div
Note on L67: date confirmation after Prod implem
Note on S67: BU (Business Unit) -> Client
Note on AC67: Dep't/Div

## Migration Request (hidden)
ISD.005.R2
Project No.
J-SOX Request No.
Migration Request |  | Applicant | Approved by | Manager
Date of application
Programs to migrate | Program Name |  | Directory
Production library name
Date of Receipt
Date for Migration
Actual Date of Migration
| Librarian | Manager | Reviewer | Log Reviewer
Note on F5: based on TIP-ISD's Project Issuing #
Note on F6: based on ME-SUI's's J-SOX System Issuing #
Note on E9: -same with Project Profile's 'AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)' [row51; columns T~AR] and 'Releasing date confirmation' [row51; columns L~R] - <name> - <date>
Note on F9: -same with Project Profile's 'SV (Supervisor) / M (Manager) -> PM (Project Manager)' [row52; columns T~AR] and 'System check-in confirmationn' [row52; columns L~R] - <name> - <date>
Note on G9: -same with Project Profile's 'M (Manager) / VP (Vice President) -> SM (Senior Project Manager)' [row53; columns T~AR] and 'Release approval (ISD)' [row53; columns L~R] - <name> - <date>
Note on D34: request receiving date
Note on D35: same date with Project Profile's 'Release approval (Client)' date (row54; columns L~R)
Note on D36: same date with Project Profile's 'Applied to Production' date (row55; colums L~R)
Note on D39: same with Project Profile's 'Applied to Production by' - ME-Sui Librarian [row55; columns T~AR] and date [row55; columns L~R] - <name> - <date>
Note on E39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>
Note on G39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>