## Issue Sheet
Issue Sheet | [17 empty] | Rev.1.0
r | Control Information
|  | Issue No. |  | TIP | I | A | 1383 | Type |  |  | Request |  | Status |  |  | OPEN
|  | Creation Date |  | 2018-10-05 |  |  |  | Due Date |  |  | 2018-10-05 |  | Close Date
|  | Priority |  | High |  |  |  | System |  |  | EBS |  | Application Module |  |  | PUR(Add-on)
r | Inquiry Information
|  | [TIP ENDUSER/TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [ME-Sui]
|  |  | Request | Approval | [5 empty] | Registration |  | Approval |  |  | Reception |  | Assignment
|  | Dept. | MPD | MPD |  |  |  |  | Dept. | TIP-ISD |  | TIP-ISD |  | Dept.
|  | Name | Y. CALUBAYAN | B. ROSARIO |  |  |  |  | Name | R. De Villa |  | C. Tapia |  | Name
|  | Date | 2018-10-05 | 2018-10-05 |  |  |  |  | Date | 2018-10-05 |  | 2018-10-05 |  | Date
|  | Issue Category |  | Application
|  | Title |  | ADDITIONAL FUNCTION UNDER OCA RESPONSIBILITY TIP PUR Purchasing Super User GUI
|  | Issue |  | Request for additional Function under OCA Responsibility: TIP PUR Purchasing Super User GUI Additional Function: * TIP-EMP Conversion Rate Entry * Import EMP (New-USD Based)
|  | Reason |  | use to convert rate and import EMP in USD Based
|  | Detail Attachment | [5 empty] | Link to Attachment Sheet
r | Investigation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Investigation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | TIP-ISD | TIP-ISD |  |  |  |  | Dept. |  |  |  |  | Dept. | MPD |  | MPD
|  | Name | R. De Villa | C. Tapia |  |  |  |  | Name |  |  |  |  | Name | Y. CALUBAYAN |  | B. ROSARIO
|  | Date | 2018-10-05 | 2018-10-05 |  |  |  |  | Date |  |  |  |  | Date | 2018-10-05 |  | 2018-10-05
|  | Cause Category |  | Spec
|  | Cause |  | See the detailed investigation result
Workaround and Countermeasure
|  | Detail Attachement | [5 empty] | Link to Attachment Sheet
r | Actual Operation Information
|  | [TIPISD/ME-Sui] | [6 empty] | [TIPISD/ME-Sui] |  |  |  |  | [TIP ENDUSER]
|  |  | Operation | Approval | [5 empty] | Confirmation |  | Approval |  |  | Confirmation |  | Approval
|  | Dept. | [6 empty] | Dept. |  |  |  |  | Dept.
|  | Name | [6 empty] | Name |  |  |  |  | Name
|  | Date | [6 empty] | Date |  |  |  |  | Date
Actual Operation
|  | Evidence Attachment | [5 empty] | Link to Attachment Sheet
Note on C6: Control number 3 digits : Site short name (TIP) + 1 digit : Control classification (I : Issue) + 1 digit : Issued from (A : TIP-site, b : Japan-site) + 5 digits : Sequence number

## Datailed Inquiry Information
Detailed Inquiry Information
| CURRENT FUNCTION OF TIP PUR Purchasing Super User GUI | NEW FUNCTION OF TIP PUR Purchasing Super User GUI
| Change Organizations | TIP-EMP Conversion Rate Entry
| New Web-EDI System Operation: Request to send RFQ data | Import EMP (New-USD Based)
| New Web-EDI System Operation: Check on RFQ Answer data | Change Organizations
| New Web-EDI System Operation: Inquiry for Not yet answer RFQ data | New Web-EDI System Operation: Request to send RFQ data
| New Web-EDI System Operation: History - RFQ Answer Data | New Web-EDI System Operation: Check on RFQ Answer data
| Price Approval List | New Web-EDI System Operation: Inquiry for Not yet answer RFQ data
| (Show Price History) | New Web-EDI System Operation: History - RFQ Answer Data
| Procurement Plan | Price Approval List
| Inventory Trend Abnormal List | (Show Price History)
| Change P/O Quantity | Procurement Plan
| VMI Operation: Purchase Order Inquiry | Inventory Trend Abnormal List
| VMI Operation: Invoice Entry | Change P/O Quantity
| VMI Operation: Invoice Change | VMI Operation: Purchase Order Inquiry
| VMI Operation: Invoice Number Change | VMI Operation: Invoice Entry
| VMI Operation: Forecast History Inquiry 1 | VMI Operation: Invoice Change
| VMI Operation: Forecast History Inquiry 2 | VMI Operation: Invoice Number Change
| VMI Operation: BPO Amendment Request | VMI Operation: Forecast History Inquiry 1
| VMI Operation: Inquiry BPO A/N | VMI Operation: Forecast History Inquiry 2
| VMI Operation: Request Sheet | VMI Operation: BPO Amendment Request
| VMI Operation: Invoice Data Entry from Web | VMI Operation: Inquiry BPO A/N
| VMI Operation: DDR Receipt Entry | VMI Operation: Request Sheet
| VMI Operation: BPO Amendment Request (Order Pattern) | VMI Operation: Invoice Data Entry from Web
| RFA Operation: Request For Adjustment Entry | VMI Operation: DDR Receipt Entry
| RFA Operation: View RFA Status | VMI Operation: BPO Amendment Request (Order Pattern)
| RFA Operation: Change Organization | RFA Operation: Request For Adjustment Entry
| Import System (IMPEX): View Shipping Status/Logistics Charges | RFA Operation: View RFA Status
| Damage Report: View Damage Report | RFA Operation: Change Organization
| Damage Report: Advanced Worklist | Import System (IMPEX): View Shipping Status/Logistics Charges
| Change Promised Date | Damage Report: View Damage Report
| Master Maintenance | Damage Report: Advanced Worklist
| VMI Operation: BPO Amendment Approval | Change Promised Date
| VMI Operation: BPO Unit Price Change | Master Maintenance
VMI Operation: BPO Amendment Approval
VMI Operation: BPO Unit Price Change
Note on D5: additional Function under TIP PUR Purchasing Super User GUI

## NEW MPD OCA RESP
Function | TIP PUR Requisitioner | TIP PUR Request for PR Approval Flow Revision | TIP PUR Staff User | TIP PUR Staff (SV/GL) User | TIP PUR Purchase Order Approval Flow Revision | TIP PUR Purchasing User | TIP PUR Purchasing Super User GUI | TIP PUR Supplier Registration | TIP PUR Supplier Manager | TIP PUR EMP | TIP PUR Staff (Planning) user | TIP AR AUTO DN/CN SYSTEM | TIP PUR System Inquiry | TIP PUR CMN System Inquiry
Request For Adjustment Entry
View RFA Status
Documents: Notifications Summary |  |  | √ | √ | [6 empty] | √
Documents: Supplier Item Category |  |  | √ | √ | [6 empty] | √
Documents: Item Search |  |  | √ | √ | [6 empty] | √
Documents: Auto Create |  |  | √ | √
Documents: Requisitions | √
Documents: Supplier Summary |  |  |  | √
Documents: Requisition Summary | √
Documents: Personal Profiles |  |  | √ | √ | [6 empty] | √
Documents: Attachments |  |  | √ | √ | [6 empty] | √
Documents: Requests |  |  | √ | √ | [6 empty] | √
Documents>Reports: Run
Documents>Reports: Set
Inquiry>Purchases: Purchases
Inquiry>Purchases: Purchase Order Summary
Inquiry>Requisitions: Requisitions
Inquiry>Requisitions: Distributions
Submit Request for PR Approval Flow Update |  | √
Item Attributes |  |  | √
Change Organizations |  |  | √ | √ |  | √ | √ |  |  |  | √
Documents>Requisitions: Requisitions Summary |  |  | √ | √ | [6 empty] | √
Documents>Requisitions: Requisition |  |  |  | √
Documents>Purchase Orders: Purchase Order Summary |  |  | √ | √ | [6 empty] | √
Documents>Purchase Orders: Purchase Orders |  |  | √ | √
Documents>Purchase Orders: Releases |  |  | √ | √ | [6 empty] | √
Documents>Purchase Orders: PO Change History |  |  | √ | √ | [6 empty] | √
Documents>Purchase Orders: Exceeded Price Tolerance |  |  | √ | √ | [6 empty] | √
Documents>Purchase Orders: Pending Purchase Order Changes |  |  | √ | √ | [6 empty] | √
Documents>Purchase Orders: Manage Deliverables |  |  | √ | √ | [6 empty] | √
Documents>RFQ's and Quotations: RFQ's |  |  | √ | √
Documents>RFQ's and Quotations: Quatations |  |  | √ | √
Documents>RFQ's and Quotations: Quate Analysis |  |  | √ | √
Documents>Reports: Run |  |  | √ | √ | [6 empty] | √
Documents>Reports: Set |  |  | √ | √ | [6 empty] | √
New Web-EDI System Operation: Request to send RFQ data |  |  | √ | √ |  |  | √ |  |  |  | √
New Web-EDI System Operation: Check on RFQ Answer data |  |  | √ | √ |  |  | √ |  |  |  | √
New Web-EDI System Operation: Inquiry for Not yet answer RFQ data |  |  | √ | √ |  |  | √ |  |  |  | √
New Web-EDI System Operation: History - RFQ Answer Data |  |  | √ | √ |  |  | √ |  |  |  | √
Item Costs: Item Costs |  |  |  | √
Item Costs: Item Cost History |  |  |  | √
Item Costs: View Costed Indented Bills |  |  |  | √
Item Costs>Standard Cost Update: Update Costs |  |  |  | √
Item Costs>Standard Cost Update: View Cost Update |  |  |  | √
Item Costs>Standard Cost Update: Purge Cost Update History |  |  |  | √
Item Costs>Standard Cost Update: View Cost History |  |  |  | √
Item Costs>Average Cost Update: Update Costs |  |  |  | √
Item Costs>Average Cost Update: Transfer Invoice Variance |  |  |  | √
Item Costs>Layer Cost Update: Update Costs |  |  |  | √
Item Category: Categories |  |  |  | √
Item Category: Sets |  |  |  | √
Item Category: Default Sets |  |  |  | √
Setup Notes: Source and Note Type Mapping |  |  |  | √
Setup Notes: Note Types |  |  |  | √
Inquiry: Vendors |  |  |  | √
Inquiry: Notifications |  |  |  | √
Inquiry>Documents>Purchases: Purchases |  |  |  | √
Inquiry>Documents>Purchases: Purchase Order Summary |  |  |  | √
Inquiry>Documents>Requisitions: Requisitions |  |  |  | √
Inquiry>Documents>Requisitions: Distributions |  |  |  | √
Inquiry>Receipts: Receipts |  |  |  | √
Inquiry>Items: Attributes |  |  |  | √
Inquiry>Items: Status |  |  |  | √
Inquiry>Items: Catalog |  |  |  | √
Inquiry>Personnel: Employee |  |  |  | √
Inquiry>Personnel: Job |  |  |  | √
Inquiry>Personnel: Position |  |  |  | √
Inquiry>Personnel: Hierarchy |  |  |  | √
TIP Reports: PUR |  |  | √ | √
Submit Request for PO Approval Flow Revision |  |  |  |  | √
Purchasing Master Maintenance | [5 empty] | √
VMI Buyer Code Registration
Price Approval List | [5 empty] | √ | √
Price Rejected/Approved | [5 empty] | √
(Show Price History) | [5 empty] | √ | √
Procurement Plan | [5 empty] | √ | √
Inventory Trend Abnormal List | [5 empty] | √ | √
Change P/O Quantity | [6 empty] | √
Request | [5 empty] | √
VMI Operation: Purchase Order Inquiry | [5 empty] | √ | √
VMI Operation: Invoice Entry | [5 empty] | √ | √
VMI Operation: Invoice Change | [5 empty] | √ | √
VMI Operation: Invoice Number Change | [5 empty] | √ | √
VMI Operation: Forecast History Inquiry 1 | [5 empty] | √ | √
VMI Operation: Forecast History Inquiry 2 | [5 empty] | √ | √
VMI Operation: BPO Amendment Request | [5 empty] | √ | √
VMI Operation: Inquiry BPO A/N | [5 empty] | √ | √
VMI Operation: Request Sheet | [5 empty] | √ | √
VMI Operation: Invoice Data Entry from Web | [5 empty] | √ | √
VMI Operation: DDR Receipt Entry | [6 empty] | √
VMI Operation: BPO Amendment Request (Order Pattern) | [5 empty] | √ | √
RFA Operation: Request For Adjustment Entry | [5 empty] | √ | √
RFA Operation: View RFA Status | [5 empty] | √ | √
RFA Operation: Change Organization | [5 empty] | √ | √
RFA Operation: CIP Subinventory Transfer Uploading
RFA Operation: LTI Subinventory Transfer Uploading
Import System (IMPEX): View Shipping Status/Logistics Charges | [5 empty] | √ | √
Damage Report: View Damage Report | [5 empty] | √ | √
Damage Report: Advanced Worklist | [5 empty] | √ | √
Change Promised Date |  |  |  | √ |  |  | √
Direct Price Uploading |  |  |  | √ | [6 empty] | √
Items Attributes |  |  |  | √ | [6 empty] | √
Master Maintenance | [6 empty] | √
TIP-EMP Conversion Rate Entry
Import EMP (New-USD Based)
VMI Operation: BPO Amendment Approval | [6 empty] | √
VMI Operation: BPO Unit Price Change | [6 empty] | √
Supplier Lot Maintenance | [5 empty] | √
Data Download for CMN User | [12 empty] | √ | √
TIP Purchasing Results | [12 empty] | √
Data Download for VMI Issue | [12 empty] | √
Inquiry | [7 empty] | √ | √
Supplier Merge | [7 empty] | √ | √
Banks | [7 empty] | √
Payment Terms | [7 empty] | √
Entry | [8 empty] | √
Search Supplier Bank Account Assignment | [8 empty] | √
EMP Menu: EMP Unit Price Inquiry | [9 empty] | √
EMP Menu: EMP Unit Price Maintenance | [9 empty] | √
EMP Menu: CSV data upload to EMP Unit Price Interface | [9 empty] | √
Items: Master Items | [10 empty] | √
Items: Organization Items | [10 empty] | √
Items: Cross References | [10 empty] | √
Items: Item Relationships | [10 empty] | √
Items: Item Search | [10 empty] | √
Items: Pending Status | [10 empty] | √
Items: Documents | [10 empty] | √
Items: Delete Items | [10 empty] | √
Items: Copy Item Attributes | [10 empty] | √
Items>Manufacturers' Part Numbers: Copy Item Attributes
Items>Manufacturers' Part Numbers: By Manufacturers | [10 empty] | √
Items>Manufacturers' Part Numbers: By Items | [10 empty] | √
Items>Manufacturers' Part Numbers: MPN Query-Only | [10 empty] | √
Items>Customer Items: Customer Items | [10 empty] | √
Items>Customer Items: Customer Item Cross References | [10 empty] | √
Items>Import: Import Items | [10 empty] | √
Items>Import: Import Item Category Assignments | [10 empty] | √
Items>Import: Import Customer Items | [10 empty] | √
Items>Import: Import Customer Item Cross References | [10 empty] | √
Items>Import: Import Item Cross References | [10 empty] | √
Items>Import: Import Related Items | [10 empty] | √
TIP Auto DN/CN: Auto Debit/Credit Notes | [11 empty] | √
TIP Auto DN/CN: View Auto Debit/Credit Notes Approval Status | [11 empty] | √
Purchase Orders: Enter Purchase Orders
Purchase Orders: Close Purchase Orders
Purchase Orders: Enter Monthly Purchase Orders
Purchase Orders: Enter Delivery Notice
Purchase Orders: Inquiry Import Result(P/O)
Purchase Orders: Inquiry Import Result(D/N)
Others: Change Organization - MRP
Others: View All Concurrent Requests
Shipping Requests: Enter Shipping Requests
Shipping Requests: Cancel Shipping Requests
Shipping Requests: Maintain ST Approval No
Inquiry: Inquiry P/O Status
Inquiry: Inquiry P/O
Inquiry: Inquiry S/R
Inquiry: Inquiry S/R Detail
Inquiry: Inquiry Packing Instructions
Batch Processes>Requests: Run All Batch Processes
Shipping Requests>Requests: Run XXOM SR Unlock
FG Warehouses: Change Organization
Items/Boms: Maintenance Assembly Item Master
Data Down Load for OM

## Detailed Investigation Result
Detailed Investigation Result
AOL Setup Sheet

## Actual Operation Evidence
Actual Operation Evidence

## Helpdesk Request
Helpdesk Request
ATTACH SCREENSHOT OF HELPDESK REQUEST.

## Project Profile (hidden)
Distribution : AP/SA - SV/M - SM - AP/SA (Keeping)
[5 empty] | Project Profile | [11 empty] | ISD.006.R0
Project ID |  |  | : | [7 empty] | Reference No :
Project name |  |  | :
Name of system |  |  | :
Start date |  |  | :
Scheduled delivery date |  |  | :
|  |  |  | Name | [8 empty] | Date
Execution |  | PL | :
Review |  | PM | :
Approval |  | SM | :
Approval from client |  | Client | :
Demand/Terms of agreement |  |  | :
Impact Analysis/Scope of work |  |  | :
Development process / Quotation / Deliverables / Quality Assurance
Development contents |  |  | : | A. Software Development
B. Maintenance [ Bug / Trouble / Recovery / Others( )]
Stage | Development Process |  |  | Quotation | [5 empty] | Development |  | Quality assurance plan
|  |  |  | Man-hours （Man-days） |  | Scheduled completion date Actual performance |  | Program volume |  |  |  | Execution by AP/SA Date confirmed |  | Reviewer (SA/SV) Date confirmed | Approved by Mgr Date approved
User Requirement Definition
General plan
Detailed plan
Coding
Unit test
Integration test
↑Enter page number if document
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | ソースファイル名 | [7 empty] | テスト仕様書兼単体テストドキュメント
Confirmation of Applying to Production
Releasing date confirmation |  |  | :
System check-in confirmation |  |  | :
Release approval (ISD) |  |  | :
Release approval （Client） |  |  | :
Applied to Production by |  |  | :
対象オブジェクト、コード、ファイル名 | [5 empty] | 別紙 | 無
※有の場合、参照先ファイルを添付
プログラムID |  | チェックイン先 | [7 empty] | 本番適用
Confirmation of Completion
Acceptance |  | (Internal)
|  | (External) | [13 empty] | (Client)
Note on L4: IS Project Issuing Number
Note on AH4: IS Helpdesk Control Number
Note on L7: > start of program modification/development or setup via backend (test environment) *same date with 'Coding' [row37; columns O~S and columns AD~AH] > setup via application - start of setup in test environment *'Coding' [row37; columns O~S] should be set to null
Note on L8: agreement between Client and TIP IS/ME SUI
Note on L10: AP (Analyst Programmer) / SA (System Analyst)
Note on AH10: Test Execution *actual exec date (can be multi/single date) *same date with 'Unit or Integration Test' [row38 or 39; columns O~S and AD~AH] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L11: SV (Supervisor) / M (Manager)
Note on AH11: Test Review *Review date (can be multi/single date) *same date with 'Unit or Integration Test' [rows 37, 38 or 39; columns AI~AM] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L12: M (Manager) / VP (Vice President)
Note on AH12: Test Approval *approval date(single date) *same date with 'Unit or Integration Test' [row 37, 38 or 39; columns AN~AR] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on L13: BU (Business Unit)
Note on AH13: Test Approval *approval date *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date
Note on I34: [o] *required [-] *not required
Note on L34: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O34: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T34: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI34: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN34: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I35: [o] *required [-] *not required
Note on L35: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O35: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T35: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI35: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN35: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I36: [o] *required [-] *not required
Note on L36: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O36: - if Dev't Process is [o], indicate the actual performance date - if Dev't Process is [-], set to [-]
Note on T36: -if Dev't Process is [o], can be set to [-] or may indicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AI36: -if Dev't Process is [o], indicate the actual confirmation date -if Dev't Process is [-], set to [-]
Note on AN36: -if Dev't Process is [o], indicate the actual approval date -if Dev't Proces s is [-], set to [-]
Note on I37: [o] *required [-] *not required
Note on L37: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O37: -if Dev't Process is [o], indicate the actual performace date *same date with 'Start date' [row7; columns L~T] *not applicable in: 'setup via application' -if Dev't Process is [-], set to [-]
Note on T37: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Start date' [row7; columns L~T] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AI37: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on AN37: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *not applicable in 'setup via application' -if Dev't Process is [-], set to [-]
Note on I38: [o] *required [-] *not required
Note on L38: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O38: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T38: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on AD38: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI38: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN38: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on I39: [o] *required [-] *not required
Note on L39: - if Dev't Process is [o], indicate the actual manhrs/days - if Dev't Process is [-], set to [-]
Note on O39: - if Dev't Process is [o], indicate the actual performance date *same date with 'Execution' [row10; columns AH~AP] - if Dev't process is [-], set to [-]
Note on T39: -if Dev't Process is [o], ndicate the count of identified affected program/application -if Dev't Process is [-], set to [-]
Note on W39: Enter implemented user test item.
Note on AD39: - if Dev't Process is [o], indicate the actual confirmation date *same date with 'Execution' [row10; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date - if Dev't process is [-], set to [-]
Note on AI39: -if Dev't Process is [o], indicate the actual confirmation date *same date with 'Review' date [row11; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on AN39: -if Dev't Process is [o], indicate the actual approval date *same date with 'Approval' date [row12; columns AH~AP] *should consider Test Script(UAT) or Test Scenario(Sign off Sheet) approval date -if Dev't Process is [-], set to [-]
Note on L51: Target Envi: Production *same date with Migration Request's 'Applicant' request date [row9; column E]
Note on T51: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on L52: Target Envi: Production *same date with Migration Request's 'Approved' date [row9; column F]
Note on T52: SV (Supervisor) / M (Manager) -> PM (Project Manager)
Note on L53: Target Envi: Production *same date with Migration Request's 'Manager' approved date [row9; column G]
Note on T53: M (Manager) / VP (Vice President) -> SM (Senior Project Manager)
Note on L54: Target Envi: Production *same date with Migration Request's 'Date for Migration' date [row35; columns D~E]
Note on T54: BU (Business Unit) -> Client
Note on L55: Target Envi: Production *same date with Migration Request's 'Actual Date of Migration' date [row36; columns D~E and row39; column D]
Note on T55: ME Sui Librarian
Note on L66: date confirmation after Prod implem
Note on S66: AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)
Note on AC66: Dep't/Div
Note on L67: date confirmation after Prod implem
Note on S67: BU (Business Unit) -> Client
Note on AC67: Dep't/Div

## Migration Request (hidden)
ISD.005.R2
Project No.
J-SOX Request No.
Migration Request |  | Applicant | Approved by | Manager
Date of application
Programs to migrate | Program Name |  | Directory
Production library name
Date of Receipt
Date for Migration
Actual Date of Migration
| Librarian | Manager | Reviewer | Log Reviewer
Note on F5: based on TIP-ISD's Project Issuing #
Note on F6: based on ME-SUI's's J-SOX System Issuing #
Note on E9: -same with Project Profile's 'AP (Analyst Programmer) / SA (System Analyst) -> PL (Project Leader)' [row51; columns T~AR] and 'Releasing date confirmation' [row51; columns L~R] - <name> - <date>
Note on F9: -same with Project Profile's 'SV (Supervisor) / M (Manager) -> PM (Project Manager)' [row52; columns T~AR] and 'System check-in confirmationn' [row52; columns L~R] - <name> - <date>
Note on G9: -same with Project Profile's 'M (Manager) / VP (Vice President) -> SM (Senior Project Manager)' [row53; columns T~AR] and 'Release approval (ISD)' [row53; columns L~R] - <name> - <date>
Note on D34: request receiving date
Note on D35: same date with Project Profile's 'Release approval (Client)' date (row54; columns L~R)
Note on D36: same date with Project Profile's 'Applied to Production' date (row55; colums L~R)
Note on D39: same with Project Profile's 'Applied to Production by' - ME-Sui Librarian [row55; columns T~AR] and date [row55; columns L~R] - <name> - <date>
Note on E39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>
Note on G39: ME-Sui Librarian's Manager Name and Approval date - <name> - <date>